## Sheet1 (hidden)
Match | ID | Title | Work Item Type | Assigned To | Time Criticality | Priority | Effort | Target Date | State | Tags | Area Path
#REF! | 165196 | Generation of manual JSON files for Langhorne | Feature | Polannagari, Govardhan | 0.5 | 2 | 2 | 2019-08-09 | Closed | Langhorne | GlobalREApps\Debt
#REF! | 65960 | EMEA data for Dublin Bank | Feature | Cole, Lisa | 8 | 1 | 1 | 2019-08-17 | Closed | _Ready; CLS; OneSource | GlobalREApps\Debt\LMW
#REF! | 127851 | Real-time data processing new loans | Feature | Talluru, Praveena | 4 | 1 | 2 | 2019-08-17 | Closed | _Ready; CLS | GlobalREApps\Debt\LMW
#REF! | 49326 | Final Concluded Property Value/LTV in Feed From Backshop to LMW | Feature | Mitchell, Aj | 3 | 1 | 3 | 2019-08-17 | Closed | _Ready; LMW | GlobalREApps\Debt\LMW
#REF! | 133868 | CLS Implementation for CECL Enhancements | Feature | Montoya, Fabio | 1.75 | 1 | 4 | 2019-08-17 | Closed | _Ready; CECL; CLS | GlobalREApps\Debt\CLS
#REF! | 133865 | Backshop Implementation for CECL Enhancements | Feature | Montoya, Fabio | 1.667 | 1 | 1 | 2019-08-17 | Closed | _Ready; Backshop; Backshop_Met; CECL | GlobalREApps\Debt\CLS
#REF! | 119226 | Client Reporting : Beneficial Borrower Report feed to SSB for CMIF loans | Feature | Bose, Siddhartha | 1.2 | 1 | 5 | 2019-08-17 | Closed | _Ready; MIS | GlobalREApps\Debt\MIS
#REF! | 49574 | Automatically generate and attach the FTM Compare Report to the the "FTM Review Approved" notification | Feature | Mitchell, Aj | 1 | 1 | 6 | 2019-08-17 | Closed | _Ready; Backshop | GlobalREApps\Debt
#REF! | 156184 | Script Request - Loan 702826 Rating and Valuation Review - Loan Commentary | Feature | Ramaraj, Vinoth | 8 | 2 | 1 | 2019-08-17 | Closed | _Ready; LMW | GlobalREApps\Debt
#REF! | 156201 | Data Script request to update mortgage rating grade for loan 540151 | Feature | Ramaraj, Vinoth | 8 | 2 | 1 | 2019-08-17 | Closed | _Ready; LMW | GlobalREApps\Debt
#REF! | 160978 | CECL - Publish MetLife Internal Ratings in Loan Rating file | Feature | Montoya, Fabio | 4 | 2 | 1 | 2019-08-17 | Closed | _Ready; CECL; MIS | GlobalREApps\Debt\CLS
#REF! | 162295 | BHF: new compliance fields for ADW | Feature | Cole, Lisa | 3 | 2 | 1 | 2019-08-17 | Closed | _Ready; CLS | GlobalREApps\Debt
#REF! | 132647 | Send an email when Hedge Type is Added/Updated/Deleted | Feature | Mitchell, Aj | 3 | 2 | 1 | 2019-08-17 | Closed | _Ready; CLS; LMW | GlobalREApps\Debt
#REF! | 144312 | The Financial Reporting category Change notification in LMW does not display the previous Financial Category | Feature | Mitchell, Aj | 2 | 2 | 1 | 2019-08-17 | Closed | _Ready; LMW | GlobalREApps\Debt
#REF! | 162296 | BHF: Change column name in ADW | Feature | Cole, Lisa | 2 | 2 | 1 | 2019-08-17 | Closed | _Ready; CLS | GlobalREApps\Debt
#REF! | 119207 | Tenant data upload error | Feature | Talluru, Praveena | 1.75 | 2 | 4 | 2019-08-17 | Closed | _Ready; LMW | GlobalREApps\Debt\LMW
#REF! | 113633 | Provide Commercial data for CECL CALCULATOR | Feature | Montoya, Fabio | 1.6 | 2 | 1 | 2019-08-17 | Closed | _Ready; Backshop; CECL; CLS; LMW; MIS; MSAS | GlobalREApps\Debt
#REF! | 61012 | CLS System Admin Permissions to Update the Origination Date | Feature | Cole, Lisa | 1.5 | 2 | 2 | 2019-08-17 | Closed | _Ready; CLS | GlobalREApps\Debt
#REF! | 61013 | Check for Month End Accruals Release Process | Feature | Cole, Lisa | 1.5 | 2 | 2 | 2019-08-17 | Closed | _Ready; CLS | GlobalREApps\Debt
#REF! | 120731 | Final Concluded Property Value/LTV in Feed From Backshop to LMW | Feature | Mitchell, Aj | 1.5 | 2 | 6 | 2019-08-17 | Closed | _Ready; Backshop; Backshop_Met | GlobalREApps\Debt\Backshop
#REF! | 84681 | Estimated Funding Date change | Feature | Anderson, William | 1.25 | 2 | 4 | 2019-08-17 | Closed | Backshop | GlobalREApps\Debt
#REF! | 159487 | CECL - Input CSV File field corrections | Feature | Montoya, Fabio | 1.25 | 2 | 4 | 2019-08-17 | Closed | _Ready; CECL; LMW | GlobalREApps\Debt\CLS
#REF! | 154691 | Allocation Reminder Notification | Feature | Anderson, William | 1 | 2 | 6 | 2019-08-17 | Closed | _Ready; Backshop | GlobalREApps\Debt
#REF! | 154707 | Rate Lock Reminder Notification | Feature | Anderson, William | 1 | 2 | 3 | 2019-08-17 | Closed | _Ready; Backshop | GlobalREApps\Debt
#REF! | 163521 | BHF Whole Loan - Loan Allocation Issue and Notification: MIM Approval Notification | Feature | Anderson, William | 1 | 2 | 5 | 2019-08-17 | Closed | Backshop | GlobalREApps\Debt\Backshop
#REF! | 136860 | Email from Loan Manager and Producer Link in LMW Loan Header does not include the Loan Number | Feature | Mitchell, Aj | 1 | 2 | 2 | 2019-08-17 | Closed | _Ready; LMW | GlobalREApps\Debt
#REF! | 144307 | Revise the highlight color coding logic in the LMW Maturity Report | Feature | Mitchell, Aj | 4 | 3 | 1 | 2019-08-17 | Closed | _Ready; LMW | GlobalREApps\Debt
#REF! | 151392 | Change GA Reportable to Delegated Authority Reportable in LMW | Feature | Mitchell, Aj | 1 | 3 | 1 | 2019-08-17 | Closed | _Ready; LMW | GlobalREApps\Debt
#REF! | 169146 | Loan Search - Report run and export issues | Feature | Polannagari, Govardhan |  | 1 |  | 2019-08-24 | Closed | Debt; High Risk; Loan Search; MIS | GlobalREApps\Debt\MIS
#REF! | 134972 | BHF : Incorrect REI Market Area & attributes in MIS and upstream systems | Feature | Polannagari, Govardhan | 2 | 1 | 4 | 2019-08-24 | Closed | _Ready; MIS | GlobalREApps\Debt\MIS
#REF! | 164350 | Subledger data break - Fix for loan#703141 | Feature | Polannagari, Govardhan |  | 2 |  | 2019-08-24 | Closed | MIS; Problem | GlobalREApps\Debt\MIS
#REF! | 145409 | Market Value : Caps and Floors Error | Feature | Polannagari, Govardhan | 4 | 2 | 1 | 2019-08-24 | Closed | _Ready; Market Value; MIS | GlobalREApps\Debt\MIS
#REF! | 142570 | MARS - Step rate loans incorrectly categorized as ARMs in MIS due to EDM field MetLifeInterestType consumption derivation logic changed. | Feature | Polannagari, Govardhan | 3 | 2 | 2 | 2019-08-24 | Closed | _Ready; MARS; MIS | GlobalREApps\Debt\MIS
#REF! | 146115 | MIS_PAMTransExtract Load Batch Job update | Feature | Polannagari, Govardhan | 2.5 | 2 | 2 | 2019-08-24 | Closed | _Ready; MIS | GlobalREApps\Debt
#REF! | 159170 | MIS : Company name issue - AVIVA Life & Pensions UK Limited | Feature | Polannagari, Govardhan | 2 | 2 | 2 | 2019-08-24 | Closed | MIS; Technical Debt | GlobalREApps\Debt\MIS
#REF! | 161675 | MIS Veracode Findings 2019 - High Flaws | Feature | Polannagari, Govardhan | 2 | 2 | 3 | 2019-08-24 | Closed | MIS; Technical Debt; Veracode | GlobalREApps\Debt\MIS
#REF! | 146600 | MIS Asset File is missing country sub div codes | Feature | Polannagari, Govardhan | 1.333 | 2 | 3 | 2019-08-24 | Closed | _Ready; EDM Sub Div Code; MIS | GlobalREApps\Debt
#REF! | 158916 | MARS : MIS consumption of TDR fields | Feature | Polannagari, Govardhan | 1.333 | 2 | 3 | 2019-08-24 | Closed | _Ready; MARS; MIS | GlobalREApps\Debt\MIS
#REF! | 166747 | Incorrect Property Type - Schedule B | Feature | Polannagari, Govardhan | 7 | 1 | 1 | 2019-09-14 | Active | _Ready; MIS; Sched B | GlobalREApps\Debt\MIS
#REF! | 173796 | MIS Domain Mapping - missing Country Admin Subdivision | Feature | Polannagari, Govardhan | 3 | 1 | 1 | 2019-09-14 | New | _Ready; MIS | GlobalREApps\Debt
#REF! | 119203 | Data at rest encryption | Feature | Polannagari, Govardhan | 2.25 | 1 | 2 | 2019-09-14 | Active | _Ready; MIS | GlobalREApps\Debt\MIS
#REF! | 87842 | Ethical Hack: Remediate PrimeOn - medium flaws – Phase 3 | Feature | Talluru, Praveena | 1.6 | 1 | 5 | 2019-09-14 | Active | _Ready; LMW | GlobalREApps\Debt\LMW
#REF! | 113622 | AG : Servicer compare report enhancement | Feature | Polannagari, Govardhan | 1.2 | 1 | 5 | 2019-09-14 | Active | _Ready; AG; MIS | GlobalREApps\Debt\MIS
#REF! | 125510 | Portfolio code expansion - Phase 1 | Feature | Cole, Lisa | 1 | 1 | 2 | 2019-09-14 | Active | _Ready; CLS; LMW | GlobalREApps\Debt\LMW
#REF! | 162142 | LMW: Create OneSource feed | Feature | Jacobs, Julie | 1 | 1 | 8 | 2019-09-14 | Active | _Ready; LMW | GlobalREApps\Debt
#REF! | 163481 | Portfolio code expansion - Phase 1 | Feature | Polannagari, Govardhan | 1 | 1 | 4 | 2019-09-14 | Active | _Ready; MIS | GlobalREApps\Debt
#REF! | 163486 | Portfolio code expansion - Phase 2 | Feature | Polannagari, Govardhan | 1 | 1 | 10 | 2019-09-14 | Active | _Ready; MIS | GlobalREApps\Debt
#REF! | 163488 | Portfolio code expansion - Phase 2 | Feature | Cole, Lisa | 0.5 | 1 | 8 | 2019-09-14 | Active | _Ready; CLS; LMW | GlobalREApps\Debt
#REF! | 159483 | LMW Actual Unfunded Amount in cube- Correct calculation | Feature | Mitchell, Aj | 7 | 2 | 1 | 2019-09-14 | Active | _Ready; LMW | GlobalREApps\Debt
#REF! | 170771 | MARS: PAM Conversion, RESI Account Reclass Sept/2019 | Feature | Polannagari, Govardhan | 3 | 2 | 1 | 2019-09-14 | Active | Debt; MARS; MIS | GlobalREApps\Debt\MIS
#REF! | 151867 | Digital Portal: Loan Ratings JSON | Feature | Polannagari, Govardhan | 1.4 | 2 | 5 | 2019-09-14 | New | _Ready; Digital Portal; Langhorne; LMW | GlobalREApps\Debt\CLS
#REF! | 144508 | Langhore: Loan Ratings JSON Implementation | Feature | Polannagari, Govardhan | 1.4 | 2 | 3 | 2019-09-14 | Active | CECL; Digital Portal; Framework; Langhorne; LMW | GlobalREApps\Debt\CLS
#REF! | 161582 | MIS Loan search - ACLI Property Type changes on report generation | Feature | Polannagari, Govardhan | 1.333 | 2 | 3 | 2019-09-14 | Active | MIS | GlobalREApps\Debt
#REF! | 162280 | MIS Veracode Findings 2019 - Medium Flaws | Feature | Polannagari, Govardhan | 1.2 | 2 | 5 | 2019-09-14 | New | MIS; Technical Debt; Veracode | GlobalREApps\Debt\MIS
#REF! | 133893 | Consumption of CECL Calculator Output File - Enchance CLS | Feature | Montoya, Fabio | 1.167 | 2 | 6 | 2019-09-14 | Active | CECL; CLS | GlobalREApps\Debt
#REF! | 144512 | Langhorne: Property JSON Implementation | Feature | Polannagari, Govardhan | 1 | 2 | 3 | 2019-09-14 | New | _Ready; Digital Portal; Framework; Langhorne | GlobalREApps\Debt\CLS
#REF! | 144513 | Digital Portal: Building JSON Implementataion | Feature | Polannagari, Govardhan | 1 | 2 | 2 | 2019-09-14 | New | Digital Portal; Framework; Langhorne | GlobalREApps\Debt\CLS
#REF! | 158888 | MIS : Quarterly Report Changes for Client Portal | Feature | Polannagari, Govardhan | 1 | 2 | 4 | 2019-09-14 | Active | _Ready; MIS | GlobalREApps\Debt\MIS
#REF! | 159105 | MIS : Charles River Code Failure fix | Feature | Polannagari, Govardhan | 1 | 2 | 2 | 2019-09-14 | Active | MIS; Technical Debt | GlobalREApps\Debt\MIS
#REF! | 122060 | MIS : Portfolio Exposure Data Dump Report Enhancement | Feature | Polannagari, Govardhan | 0.778 | 2 | 9 | 2019-09-14 | Active | _Ready; MIS | GlobalREApps\Debt\MIS
#REF! | 155876 | Backshop Field Extract for MIST | Feature | Anderson, William |  | 2 | 8 | 2019-09-20 | Active | Backshop | GlobalREApps\Debt\Backshop
#REF! | 162136 | FTP Activities for Backshop Field Extract for MIST | Feature | Anderson, William |  | 2 | 3 | 2019-09-20 | New | Backshop; Backshop_Met | GlobalREApps\Debt
#REF! | 156000 | Revisions and additions to the REI Market Area reference data_Backshop | Feature | Mitchell, Aj | 3 | 2 | 2 | 2019-09-20 | Active | _Ready; Backshop | GlobalREApps\Debt
#REF! | 150715 | Increase the Commitment Fee (BPS) field size from 1 decimal to 2 decimal places in MIM notification | Feature | Anderson, William | 3 | 2 | 1 | 2019-09-20 | New | _Ready; Backshop | GlobalREApps\Debt
#REF! | 160505 | BackShop Audit file generation delays | Feature | Anderson, William | 1.333 | 2 | 3 | 2019-09-20 | New | Backshop; Backshop_Met; Japan Item | GlobalREApps\Debt
#REF! | 113634 | Calculate Relative Value for Comm and AG Assets | Feature | Mitchell, Aj | 1.167 | 2 | 6 | 2019-09-20 | Active | _Spike; Backshop; Backshop_Met | GlobalREApps\Debt
#REF! | 61014 | Capitalized Interest Transactions | Feature | Cole, Lisa | 0.8333 | 2 | 6 | 2019-09-20 | New | _Spike; CLS | GlobalREApps\Debt
#REF! | 160836 | Insert New REI Market Areas and revise several existing | Feature | Polannagari, Govardhan |  | 2 |  | 2019-09-21 | New | LMW | GlobalREApps\Debt
#REF! | 143186 | SFR loans to CLS from Midland | Feature | Lopez, Ascension | 1.333 | 1 | 4 | 2019-09-27 | New | _Ready; CLS | GlobalREApps\Debt
#REF! | 161827 | Discovery: Move calculation of price from MIS to LMW | Feature | Mitchell, Aj | 2.667 | 1 | 3 | 2019-09-28 | New | _Spike; LMW | GlobalREApps\Debt
#REF! | 149953 | Discovery: Add a new data field for Investor Summary Commentary in LMW Watchlist comments control | Feature | Mitchell, Aj | 2.33 | 1 | 3 | 2019-09-28 | New | _Spike; LMW; MIM Client Portal | GlobalREApps\Debt
#REF! | 163297 | EMEA data for Dublin Bank - Paid in full loans | Feature | Cole, Lisa | 1.333 | 1 | 3 | 2019-09-28 | New | _Ready; CLS; OneSource | GlobalREApps\Debt\LMW
#REF! | 144510 | Langhorne: Transactions JSON Implementation | Feature | Polannagari, Govardhan | 1 | 2 | 2 | 2019-09-28 | New | _Ready; CLS; Digital Portal; Framework; Langhorne | GlobalREApps\Debt\CLS
#REF! | 144511 | Langhorne: Commitment JSON Implementation | Feature | Polannagari, Govardhan | 1 | 2 | 6 | 2019-09-28 | New | CECL; Digital Portal; Framework; Langhorne | GlobalREApps\Debt\CLS
#REF! | 151869 | Langhorne: Property Valuation JSON | Feature | Polannagari, Govardhan | 1 | 2 | 4 | 2019-09-28 | New | _R; Digital Portal; Langhorne; MIS | GlobalREApps\Debt
#REF! | 151727 | Langhorne - Asset (Loan) Masters JSON NEW ELEMENTS to EDM | Feature | Polannagari, Govardhan | 1.286 | 1 | 7 | 2019-10-05 | New | Digital Portal; Langhorne | GlobalREApps\Debt
#REF! | 161828 | Phase 1: Move calculation of price from MIS to LMW | Feature | Mitchell, Aj | 1.2 | 1 | 5 | 2019-10-05 | New | LMW | GlobalREApps\Debt
#REF! | 163491 | Portfolio code expansion - Phase 3 | Feature | Cole, Lisa | 1 | 1 | 4 | 2019-10-05 | New | _Ready; CLS; LMW | GlobalREApps\Debt
#REF! | 163497 | Portfolio code expansion - Phase 3 | Feature | Polannagari, Govardhan | 1 | 1 | 6 | 2019-10-05 | Active | _Ready; MIS | GlobalREApps\Debt
#REF! | 165192 | Langhorne ME - Asset Rating JSON | Feature | Polannagari, Govardhan | 2 | 2 | 3 | 2019-10-05 | New | CLS; Langhorne; LMW | GlobalREApps\Debt
#REF! | 165193 | Langhorne ME - Property Valuation JSON | Feature | Polannagari, Govardhan | 2 | 2 | 3 | 2019-10-05 | New | CLS; Langhorne; LMW | GlobalREApps\Debt
#REF! | 165194 | Langhorne ME - Position JSON | Feature | Polannagari, Govardhan | 2 | 2 | 3 | 2019-10-05 | New | CLS; Langhorne; LMW | GlobalREApps\Debt
#REF! | 165934 | Enrich NLS with new data elements | Feature | Anderson, William | 1.5 | 2 | 4 | 2019-10-05 | New | _Spike; Backshop; Backshop_Met; MarkIT EDM | GlobalREApps\Debt
#REF! | 165191 | Langhorne ME - Asset Master JSON | Feature | Polannagari, Govardhan | 1.2 | 2 | 5 | 2019-10-05 | New | CLS; Langhorne; LMW | GlobalREApps\Debt
#REF! | 164302 | Enhance Backshop/CLS/LMW systems to capture and store new data elements. | Feature | Polannagari, Govardhan | 1 | 2 | 5 | 2019-10-05 | New | CLS; Langhorne; LMW | GlobalREApps\Debt
#REF! | 165935 | Enrich NLS with new data elements | Feature | Mitchell, Aj | 0.86 | 2 | 7 | 2019-10-05 | New | _Ready; LMW | GlobalREApps\Debt
#REF! | 162327 | Production Support - PI 2 2019 Debt | Feature | Hopper, Jeff | 1 | 1 | 10 | 2019-10-08 | New | Backshop_Met; CLS; LMW; MIS | GlobalREApps\Debt
#REF! | 165243 | Adding new balance fields in MIS for CECL Accounting and consume in MIS from CLS & MSAS (Phase 2) | Feature | Montoya, Fabio | 1 | 1 | 3 | 2019-10-08 | New | CECL; CLS; MIS | GlobalREApps\Debt\CLS
#REF! | 165245 | Generation of CECL Active Loans Accounting entries out of CLS(Phase 2) | Feature | Montoya, Fabio | 0.889 | 1 | 6 | 2019-10-08 | New | CECL; CLS | GlobalREApps\Debt\CLS
#REF! | 161232 | Adding new balance fields in CLS for CECL Accounting and publish to MIS (Phase 1) | Feature | Montoya, Fabio | 0.75 | 1 | 5 | 2019-10-08 | New | CECL; CLS | GlobalREApps\Debt\CLS
#REF! | 166870 | CECL - Additional corrections in CSV Input feed | Feature | Montoya, Fabio |  | 2 | 3 | 2019-10-08 | New | CECL; LMW | GlobalREApps\Debt\CLS
#REF! | 144514 | Langhorne: Amortization Schedule in JSON Implementation | Feature | Soundararajan, Madhan Kumar | 1 | 2 | 2 | 2019-10-08 | Active | Langhorne | GlobalREApps\Debt\CLS
#REF! | 150749 | Discovery - Make non REI managed loans viewable | Feature | Mitchell, Aj | 1 | 2 | 3 | 2019-10-08 | New | _Spike; LMW | GlobalREApps\Debt
#REF! | 120687 | Chile Commercial mortgages data for input into calculator | Feature | Montoya, Fabio | 3 | 3 | 1 | 2019-10-08 | New | CECL; LMW | GlobalREApps\Debt\CLS
#REF! | 161707 | Chile Commercial mortgages data for outbound into calculator | Feature | Montoya, Fabio | 3 | 3 | 1 | 2019-10-08 | New | CECL; LMW | GlobalREApps\Debt\CLS

## Start Here
| PI Sprint # | Cloud Services Sprint # | Start Date | End Date | Release | PI-Sprint | Env | Abbrev | Start Date | End Date | Red = Holiday
PI-8 Sprint Dates | 5 | 96 | 2022-03-23 | 2022-04-05 | April 2022 | (PI-8) 3-5 | DEV | DA | 2022-02-28 | 2022-03-25 |  | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S
| 6 | 97 | 2022-04-06 | 2022-04-19 |  | (PI-8) 5-6 | SIT/INT | SA | 2022-03-28 | 2022-04-01 | April | [5 empty] | 1 | 2 | May | 1 | 2 | 3 | 4 | 5 | 6 | 7
PI-9 Sprint Dates | 1 | 98 | 2022-04-20 | 2022-05-03 |  | (PI-8) 6 | UAT/QA | UA | 2022-04-04 | 2022-04-12 | [6 empty] | SA, UA, DY | SA, UA, DY |  | SY,UY | UY,DU | UY,DU | UY,DU | UY,DU | UY,DU | UY,DU
| 2 | 99 | 2022-05-04 | 2022-05-17 |  | (PI-9) 1 | PROD+DR | PA | 2022-04-16 |  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14
| 3 | 100 | 2022-05-18 | 2022-05-31 | May 2022 | (PI-8) 5-6 (PI-9) 1 | DEV | DY | 2022-03-28 | 2022-04-22 |  | SA, UA, DY | UA, DY | UA, DY | UA, DY | UA, DY | UA, DY | UA, DY |  | UY,DU | UY,DU | UY,DU | PY,DU | PY,DU | PY,DU | PY,DU
| 4 | 101 | 2022-06-01 | 2022-06-14 |  | (PI-9) 1 | SIT/INT | SY | 2022-04-25 | 2022-04-29 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 15 | 16 | 17 | 18 | 19 | 20 | 21
| 5 | 102 | 2022-06-15 | 2022-06-28 |  | (PI-9) 1-2 | UAT/QA | UY | 2022-05-02 | 2022-05-10 |  | UA, DY | UA, DY | UA, DY | PA,DY | PA,DY | PA,DY | PA,DY |  | DU | DU | DU | DU | DU | DU | DU
| 6 | 103 | 2022-06-29 | 2022-07-12 |  | (PI-9) 3 | PROD+DR | PY | 2022-05-14 |  |  | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 22 | 23 | 24 | 25 | 26 | 27 | 28
PI-10 | 1 | 104 | 2022-07-13 | 2022-07-26 | June 2022 | (PI-9) 1-3 | DEV | DU | 2022-05-02 | 2022-05-27 |  | DY | DY | DY | DY | DY | DY,SY | DY,SY |  | DU | DU | DU | DU | DU | DU,SU | DU,SU
| 2 | 105 | 2022-07-27 | 2022-08-09 |  | (PI-9) 3 | SIT/INT | SU | 2022-05-30 | 2022-06-03 |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | 29 | 30 | 31
[6 empty] | (PI-9) 3-4 | UAT/QA | UU | 2022-06-06 | 2022-06-14 |  | DY,SY | SY | SY | SY | SY | SY,UY | SY,UY |  | DU,SU | SU,DL | SU,DL
[6 empty] | (PI-8) 4 | PROD+DR | PU | 2022-06-18
[5 empty] | July 2022 | (PI-8) 3-5 | DEV | DL | 2022-05-30 | 2022-06-24
[6 empty] | (PI-8) 5-6 | SIT/INT | SL | 2022-06-27 | 2022-07-01
[6 empty] | (PI-8) 6 | UAT/QA | UL | 2022-07-04 | 2022-07-12 |  | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S
|  |  | Planned | Available=Actual - Holidays |  | (PI-9) 1 | PROD+DR | PL | 2022-07-16 |  | June |  |  |  | 1 | 2 | 3 | 4 | July | [5 empty] | 1 | 2
|  |  | 74 |  | Aug 2022 | (PI-8) 5-6 (PI-9) 1 | DEV | DG | 2022-07-04 | 2022-07-29 |  |  |  |  | SU,DL | SU,DL | SU,UU,DL | SU,UU,DL | [6 empty] | SL,UL | SL,UL
[6 empty] | (PI-9) 1-2 | SIT/INT | SG | 2022-08-01 | 2022-08-05 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9
[6 empty] | (PI-9) 2 | UAT/QA | UG | 2022-08-08 | 2022-08-16 |  | SU,UU,DL | UU,DL | UU,DL | UU,DL | UU,DL | UU,DL | UU,DL |  | SL,UL | UL,DG | UL,DG | UL,DG | UL,DG | UL,DG | UL,DG
[6 empty] | (PI-9) 3 | PROD+DR | PG | 2022-08-20 |  |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
[12 empty] | UU,DL | UU,DL | UU,DL | PU,DL | PU,DL | PU,DL | PU,DL |  | UL,DG | UL,DG | UL,DG | PL,DG | PL,DG | PL,DG | PL,DG
[5 empty] | Abbreviations | Environments | Months |  |  |  |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 |  | 17 | 18 | 19 | 20 | 21 | 22 | 23
|  |  | Ninjas | Samurais | (Legend) |  | J = January |  | L = July |  |  | DL | DL | DL | DL | DL | DL,SL | DL,SL |  | DG | DG | DG | DG | DG | DG | DG
1 | 2022-04-20 | 2022-05-03 | sprint 59 | Sprint 98 |  | D = Dev | F = February |  | G = August |  |  | 26 | 27 | 28 | 29 | 30 |  |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30
2 | 2022-05-04 | 2022-05-17 | sprint 60 | Sprint 99 |  | S = SIT/INT | M = March |  | S = September |  |  | DL,SL | SL | SL | SL | SL |  |  |  | DG | DG | DG | DG | DG | DG,SG | DG,SG
3 | 2022-05-18 | 2022-05-31 | sprint 61 | Sprint 100 |  | U = UAT/QA | A = April |  | O = October | [10 empty] | 31
4 | 2022-06-01 | 2022-06-14 | sprint 62 | Sprint 101 |  | P = PROD+DR | Y = May |  | N = November | [10 empty] | DG,SG
5 | 2022-06-15 | 2022-06-28 | sprint 63 | Sprint 102 |  |  | U = June |  | D = December
6 | 2022-06-29 | 2022-07-12 | sprint 64 | Sprint 103 | [7 empty] | S | M | T | W | T | F | S
[11 empty] | August |  | 1 | 2 | 3 | 4 | 5 | 6
[6 empty] | 14 | 14
[6 empty] | 13 | 1 |  |  |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 13
swapna | 2022-01-11 | 1 |  |  |  | 1 | 5
abhijith | [11 empty] | 14 | 15 | 16 | 17 | 18 | 19 | 20
Krishna
Prasob | 1/24,2/18 | 2 | [9 empty] | 21 | 22 | 23 | 24 | 25 | 26 | 27
lokesh | 1/27,28; 2/14,15; | 4
manoj | [11 empty] | 28 | 29 | 30 | 31
smba | 1/17,18; march 5 days | 7
Aravind
Ashish
Anoop
Abdul Hanan
Mala
Vijay
Pradeep
Formulas:
Start Date = [Start Date, row above]+14
Start Date = [Start Date, row below]-12
End Date = [Start Date, row below]-4

## Resource Planning
| End Date |  |  | 2022-04-06 | 2022-04-20 | 2022-05-04 | 2022-05-18 | 2022-06-01 | 2022-06-15 | 2022-06-29 |  |  | Black Widow
|  | Name | Team | Allotment | S1 | S2 | S3 | S4 | S5 | S6 |  |  | Captain America |  |  | Commit
| AJ | Abhijith Jayakumar | The Ninjas | 1 | 0.9 | 1 | 0.9 | 1 | 1 | 1 | 46.4 | 46.4 | Hulk |  |  | Resolved
| JB | Jagadeesan Balasubramanian | The Ninjas | 1 | 1 | 1 | 0.9 | 1 | 1 | 0.9 | 46.4 | 46.4 | Ironman |  |  | Stretch
11 | KCK | Krishna chandar kandula | The Ninjas | 1 | 0.9 | 1 | 1 | 1 | 1 | 1 | 47.2 | 47.2 | Vision |  |  | Vendor
| KN | Krishnaraj Nagaraj | The Ninjas | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 43.2 | 43.2
| LS | Lokeshwaran Sankar | The Ninjas | 1 | 0.9 | 1 | 1 | 1 | 1 | 1 | 47.2 | 47.2
| MM | Manoj Madhavan | The Ninjas | 1 | 0.7 | 0.9 | 0.9 | 1 | 1 | 1 | 44 | 44 |  |  |  |  | SAMURAIS | [11 empty] | NINJAS
| MHA | Meraj Husen Ansari | The Ninjas | 1 | 0.9 | 1 | 1 | 1 | 1 | 1 | 47.2 | 47.2 |  |  |  |  | AN | AM | ASU | DF | JR | KN | MN | RB | VS | VG | AC | VA | AJ | JB | KCK | KN | LS | MM | MHA | PN | SSRP | SS | SwM | VS | DF
| PN | Prasob Nambuthodiyil | The Ninjas | 1 | 0.8 | 1 | 1 | 1 | 1 | 1 | 46.4 | 46.4 |  |  | Apr | 20 | bar: SAMURAIS AN to NINJAS DF
| SSRP | Samba siva rao prudhivi | The Ninjas | 1 | 0.9 | 1 | 1 | 1 | 1 | 1 | 47.2 | 47.2 |  |  |  | 21
| SS | Shibu Swaminathan (repl) | The Ninjas | 1 | 0.9 | 1 | 1 | 1 | 1 | 1 | 47.2 | 47.2 |  |  |  | 22 | bar: SAMURAIS AN to NINJAS DF
| SwM | Swapna Madhu | The Ninjas | 1 | 0.9 | 1 | 1 | 1 | 1 | 1 | 47.2 | 47.2 |  |  |  | 23
| VS | Varun Sundar | The Ninjas | 0.2 | 0.2 | 0.2 | 0.18 | 0.2 | 0.2 | 0.18 | 9.28 | 9.28 |  |  |  | 24
| DF | Dana Fillhart | The Ninjas | 0.4 | 0.4 | 0.4 | 0.36 | 0.4 | 0.28 | 0.36 | 17.6 | 17.6 |  |  |  | 25
12 | AN | Abdul Naik | Samurai | 1 | 0.8 | 0.7 | 1 | 1 | 1 | 1 | 44 | 44 |  |  |  | 26 | bar: SAMURAIS AN to NINJAS DF
| AM | Anoop Mohan | Samurai | 1 | 0.8 | 0.7 | 1 | 1 | 1 | 1 | 44 | 44 |  |  |  | 27 | bar: SAMURAIS AN to NINJAS DF
| ASU | Aravind Syama Unni | Samurai | 1 | 0.9 | 1 | 1 | 0.8 | 1 | 1 | 45.6 | 45.6 |  |  |  | 28
| DF | Dana Fillhart | Samurai | 0.6 | 0.6 | 0.6 | 0.54 | 0.6 | 0.42 | 0.54 | 26.4 | 26.4 |  |  |  | 29 | bar: SAMURAIS AN to NINJAS DF
| JR | Johnson Robin | Samurai | 1 | 0.8 | 1 | 1 | 1 | 1 | 1 | 46.4 | 46.4 | bar: SAMURAIS AN to NINJAS DF
| KN | Krishnaraj Nagarajan | Samurai | 0.1 | 0.1 | 0.1 | 0.09 | 0.1 | 0.1 | 0.09 | 4.64 | 4.64
| MN | Mala Nadar | Samurai | 1 | 0.9 | 1 | 0.9 | 0.7 | 1 | 1 | 44 | 44 |  |  | May | 2 | SAMURAIS AN: AN; SAMURAIS AM: AM; SAMURAIS ASU: ASU; SAMURAIS JR: JR; SAMURAIS RB: RB; NINJAS AJ: AJ; NINJAS KCK: KCK; NINJAS LS: LS; NINJAS MM: MM; NINJAS MHA: MHA; NINJAS PN: PN; NINJAS SSRP: SSRP; NINJAS SS: SS; NINJAS SwM: SwM
| RB | Rahul Bishnoi | Samurai | 1 | 0.6 | 1 | 1 | 1 | 1 | 1 | 44.8 | 44.8 |  |  |  | 3 | SAMURAIS AN: AN; SAMURAIS AM: AM; SAMURAIS JR: JR; SAMURAIS MN: MN; SAMURAIS RB: RB; SAMURAIS AC: AC; SAMURAIS VA: VA
| VS | Varun Sundar | Samurai | 0.8 | 0.8 | 0.8 | 0.72 | 0.8 | 0.8 | 0.72 | 37.12 | 37.12 |  |  | May | 4 | bar: SAMURAIS AN to NINJAS DF
| VG | Vilasini Ganesan | Samurai | 1 | 1 | 1 | 0.9 | 1 | 1 | 0.9 | 46.4 | 46.4 |  |  |  | 5 | bar: SAMURAIS AN to NINJAS DF
| AC | Ashish Chourey | Samurai | 1 | 0.8 | 1 | 1 | 1 | 1 | 1 | 46.4 | 46.4 |  |  |  | 6 | bar: SAMURAIS AN to NINJAS DF
| VA | Vijay Amirtharaj | Samurai | 1 | 0.9 | 1 | 0.9 | 0.7 | 1 | 1 | 44 | 44
[10 empty] | what does 1,2,3,5 SP mean? | [5 empty] | 9
[10 empty] | 1- 1-10 | [5 empty] | 10 | bar: SAMURAIS AN to NINJAS DF
[10 empty] | 2 -10-30 | [5 empty] | 11
[10 empty] | 3 -30-50 | [5 empty] | 12
[10 empty] | 5 - 50-70 | [5 empty] | 13
[10 empty] | 8- >70 |  |  |  | 672
[10 empty] | 9.6 | 7 | 10
16
17
[15 empty] | May | 18
[12 empty] | 38.4 |  |  |  | 19
20 | bar: SAMURAIS AN to NINJAS DF
23 | bar: SAMURAIS AN to NINJAS DF
24
25 | bar: SAMURAIS AN to NINJAS DF
26
27
[11 empty] | Sprint 1 | 2022-04-20 |  | 2022-05-03
[11 empty] | Sprint 2 | 2022-05-04 |  | 2022-05-17
[11 empty] | Sprint 3 | 2022-05-18 |  | 2022-05-31 |  | 30
[11 empty] | Sprint 4 | 2022-06-01 |  | 2022-06-14 |  | 31 | SAMURAIS DF: DF; SAMURAIS KN: KN; SAMURAIS MN: MN; SAMURAIS VS: VS; SAMURAIS VG: VG; NINJAS JB: JB; NINJAS VS: VS; NINJAS DF: DF
[11 empty] | Sprint 5 | 2022-06-15 |  | 2022-06-28 | Jun | 1 | bar: SAMURAIS AN to NINJAS DF
[11 empty] | Sprint 6 | 2022-06-29 |  | 2022-07-12 |  | 2 | bar: SAMURAIS AN to NINJAS DF
3 | bar: SAMURAIS AN to NINJAS DF
6
7
8 | bar: SAMURAIS AN to NINJAS DF
[16 empty] | 9 | SAMURAIS ASU: ASU; SAMURAIS VA: VA
[16 empty] | 10 | SAMURAIS ASU: ASU; SAMURAIS VA: VA
13
14
[15 empty] | Jun | 15
16
17
20
21 | bar: SAMURAIS AN to NINJAS DF
22 | bar: SAMURAIS AN to NINJAS DF
23 | bar: SAMURAIS AN to NINJAS DF
24
27
28
[15 empty] | Jun | 29
30
[15 empty] | Jul | 1
[16 empty] | 4 | SAMURAIS DF: DF; SAMURAIS KN: KN; SAMURAIS VS: VS; SAMURAIS VG: VG; NINJAS JB: JB; NINJAS VS: VS; NINJAS DF: DF
5
6
7
8
11
12

## ResourceAllocationByPriority
Core | [7 empty] | PI-8 Samurai Work Items - Boards (azure.com)
[8 empty] | Resource | Story points total till 7/12 |  | Product description | Product Release | Priority # |  | Samurai Resource | Available Hours: Pulled from Resource Planning till 7/12 DO NOT EDIT
|  |  | NinJa Sprint | Sprint DevOps | Sprint PI |  |  | Abhijith Jayakumar | 46.4 | [5 empty] | Abdul Naik | 44
|  |  | 59 | 98 | 1 |  |  | Jagadeesan Balasubramanian | 46.4 |  | BAU | PROOF | 1 |  | Anoop Mohan | 44
|  |  | 60 | 99 | 2 |  |  | Krishna chandar kandula | 47.2 |  | BAU | GRID | 1 |  | Aravind Syama Unni | 45.6
|  |  | 61 | 100 | 3 |  |  | Krishnaraj Nagaraj | 43.2 |  | BAU | DOS | 1 |  | Dana Fillhart | 26.4
|  |  | 62 | 101 | 4 |  |  | Lokeshwaran Sankar | 47.2 |  | BAU | IDC | 1 |  | Johnson Robin | 46.4
|  |  | 63 | 102 | 5 |  |  | Manoj Madhavan | 44 |  |  | ADJ | 1 |  | Krishnaraj Nagarajan | 4.64
|  |  | 64 | 103 | 6 |  |  | Meraj Husen Ansari | 47.2 |  |  | Databricks Optimization | 2 |  | Mala Nadar | 44
[8 empty] | Prasob Nambuthodiyil | 46.4 |  |  | IDC2 | 2.1 |  | Rahul Bishnoi | 44.8
[8 empty] | Samba siva rao prudhivi | 47.2 |  |  | GDV | 2.1 |  | Varun Sundar | 37.12
[8 empty] | Shibu Swaminathan (repl) | 47.2 |  |  | DOS RESI | 2.1 |  | Vilasini Ganesan | 46.4
[8 empty] | Swapna Madhu (Bishva) | #N/A |  |  | DOS QA Automation | 2.3 |  | Ashish Chourey | 46.4
[12 empty] | GRID QA Automation | 2.3 |  | Vijay Amirtharaj | 44
[12 empty] | Rewiring | 3 |  | UNASSIGNED | #N/A
[12 empty] | Historical Load | 3.1
[12 empty] | Future State Data project | 3.2
[12 empty] | Release on Demand | 3.3
[12 empty] | DOS RE Equity | 3.4
| Combined Available story points total till 4/15 | Actual story points total til 4/15
| Resource | (Pulled from the Resource Planning tab - DO NOT EDIT) | GDV | GRID | GRIDAdjustments | GRIDTestAutomation | IDC | IDC2 | Rewiring | DOS BAU | MIS Refactoring | ResidentialLoans | DatabricksPlatformOptimization | IDC Rewiring | RE Equity | Release-on-Demand | TechDebt | Untagged
| Abdul Naik | 44
| Anoop Mohan | 44
| Aravind Syama Unni | 45.6
| Dana Fillhart | 26.4
| Johnson Robin | 46.4
| Krishnaraj Nagarajan | 4.64
| Mala Nadar | 44
| Rahul Bishnoi | 44.8
| Varun Sundar | 37.12
| Vilasini Ganesan | 46.4
| Ashish Chourey | 46.4
| Vijay Amirtharaj | 44
| UNASSIGNED | #N/A
93,94,95
lot of work tracking
[10 empty] | Tags (Column M) | [35 empty] | Core Data Services
[15 empty] | Vilasini/Krishnaraj/Dana to discuss for IDC 2 |  |  | (need placeholders for rewiring and GDV) | [27 empty] | Core Data Services\Cloud Services
[15 empty] | Core Data Services\Cloud Services |  |  | 93,94,95 |  |  |  | 95 | [11 empty] | Krishnaraj to talk to Varun for IDC2 API stories
|  | 70% | IDC2 | 93,94 |  | 35% | IDC2 |  |  |  | 93,94 |  |  | IDC2 | 40% |  |  | Core Data Services\Cloud Services |  |  |  | 5% for calls and IDC |  |  |  | 93,94,95,97 |  |  |  | 93,94,97 |  |  |  | 93 |  |  |  | 93,94,95,97 |  |  |  |  | 65 story points |  |  | 154 SP |  |  |  | 54 Unassigned points
[34 empty] | 20% | IDC2 | [7 empty] | 93,94,95,96
|  | Abdul Naik |  |  |  | Anoop Mohan |  |  |  | Aravind Syama Unni |  |  |  | Dana Fillhart |  |  |  | Johnson Robin |  |  |  | Krishnaraj Nagarajan |  |  |  | Mala Nadar |  |  |  | Rahul Bishnoi |  |  |  | Varun Sundar |  |  |  | Vilasini Ganesan |  |  |  | Ashish Chourey |  |  |  | Vijay Amirtharaj |  |  |  | UNASSIGNED |  |  |  |  | Dependency | Total SP ask | Total SP assigned | % complete
| Product Releasae | Percentage (30%) | Available | Actual | Diff | Percentage (65%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (60%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (10%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (80%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (60%) | Available | Actual | Diff | Percentage | Available | Actual | Diff
C o r e D a t a S e r v I c e s (S a m u r a I s) | PROOF | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | VG , need scope and story
| GRID | 10% | 4.4 | 0 | 4.4 | 15% | 6.6 | 0 | 6.6 | 15% | 6.6 | 0 | 6.6 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 20% | 8.8 | 0 | 8.8 | 15% | 6.6 | 0 | 6.6 | 15% | 6.6 | 0 | 6.6 | 30% | 13.2 | 0 | 13.2 | 30% | 13.2 | 0 | 13.2 | 0 | 0 | 0 | 0 | 74.8
| DOS | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 30% | 13.2 | 0 | 13.2 | 10% | 4.4 | 0 | 4.4 | 20% | 8.8 | 0 | 8.8 | 5% | 2.2 | 0 | 2.2 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.4
| IDC | 20% | 8.8 | 0 | 8.8 | 10% | 4.4 | 0 | 4.4 | 20% | 8.8 | 0 | 8.8 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 5% | 2.2 | 0 | 2.2 | 40% | 17.6 | 0 | 17.6 | 30% | 13.2 | 0 | 13.2 | 0% | 0 | 0 | 0 | 25% | 11 | 0 | 11 | 20% | 8.8 | 0 | 8.8 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.8
| ADJ | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 5% | 2.2 | 0 | 2.2 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 20% | 8.8 | 0 | 8.8 | 10% | 4.4 | 4 | 0.4 | 0 | 0 | 0 | 0 | 20.2
| Databricks Optimization | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 50% | 22 | 0 | 22 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.4
| IDC2 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 5% | 2.2 | 0 | 2.2 | 0% | 0 | 0 | 0 | 5% | 2.2 | 0 | 2.2 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | QA team over allocation in excess of 100, ignore negative capacity. Excluding QA , we have 50+ additional SPs
| GDV | 0% | 0 | 0 | 0 | 30% | 13.2 | 0 | 13.2 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 50% | 22 | 0 | 22 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 40% | 17.6 | 0 | 17.6 | 0% | 0 | 0 | 0 | 25% | 11 | 0 | 11 | 20% | 8.8 | 0 | 8.8 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77
| DOS RESI | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 5% | 2.2 | 0 | 2.2 | 5% | 2.2 | 0 | 2.2 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 5% | 2.2 | 0 | 2.2 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 20% | 8.8 | 21 | -12.2 | 0 | 0 | 0 | 0 | -1.2
| DOS QA Automation | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Varun/Dana, Create stories to support the buffer
| GRID QA Automation | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | VG , need scope and story
| Rewiring | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 5% | 2.2 | 0 | 2.2 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.8
| Historical Load | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.8
| Future State Data project | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 20% | 8.8 | 0 | 8.8 | 5% | 2.2 | 0 | 2.2 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 10% | 4.4 | 0 | 4.4 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.2
| Release on Demand | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 5% | 2.2 | 0 | 2.2 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2
| DOS RE Equity | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 5% | 2.2 | 0 | 2.2 | 0% | 0 | 0 | 0 | 0% | 0 | #VALUE! | #VALUE! | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE!
|  | Abhijith Jayakumar |  |  |  | Prasob Nambuthodiyil |  |  |  | Manoj Madhavan |  |  |  | Krishna chandar kandula |  |  |  | Samba siva rao prudhivi |  |  |  | Swapna Madhu |  |  |  | Jagadeesan Balasubramanian |  |  |  | Krishnaraj Nagaraj |  |  |  | Meraj Husen Ansari |  |  |  | Abdul Naik |  |  |  | Anoop Mohan |  |  |  | Shibu Swaminathan (repl) |  |  |  | Lokeshwaran Sankar
Shared Services (NINJAs) | Product Releasae | Percentage (100%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage (70%) | Available | Actual | Diff | Percentage (35%) | Available | Actual | Diff | Percentage (100%) | Available | Actual | Diff | Percentage | Available | Actual | Diff
| PROOF BAU | 50% | 23.2 |  | 23.2 | 30% | 13.92 |  | 13.92 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 20% | 9.44 |  | 9.44 | 70% | 32.48 |  | 32.48 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 20% | 9.44 |  | 9.44 | 15% | 7.08 |  | 7.08 | 95.56
| Adj | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 25% | 11 |  | 11 | 0% | 0 |  | 0 | 20% | 9.44 |  | 9.44 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 20% | 9.44 |  | 944% | 29.88
| IDC | 50% | 23.2 |  | 23.2 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 20% | 9.44 |  | 9.44 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 15% | 7.08 |  | // | 32.64
| IDC2 | 0% | 0 |  | 0 | 70% | 32.48 |  | 32.48 | 75% | 33 |  | 33 | 100% | 47.2 |  | 47.2 | 80% | 37.76 |  | 37.76 | 60% | 28.32 |  | 28.32 | 0% | 0 |  | 0 | 100% | 43.2 |  | 43.2 | 100% | 47.2 |  | 47.2 | 70% | 30.8 |  | 30.8 | 35% | 15.4 |  | 15.4 | 0% | 0 |  | 0 | 50% | 23.6 |  | 23.6 | 338.96
| iRIDER | 0% | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0 |  |  | 30% | 13.92 |  | 13.92 | 0% | 0 |  |  | 0% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 80% | 37.76 |  | 37.76 | 0% | 0 |  | 0 | 51.68
| Future State Data project | 0% | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0% | 0 |  |  | 30% | 13.92 |  | 13.92 | 0% | 0 |  |  | 0% | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 80% | 37.76 |  | 37.76 | 0% | 0 |  | 0
DONOT Delete below values
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18

## Sheet2
|  |  |  | Samurais: Proportional Available Hours - Sprints 1-6 | Samurais - Proportional Actual hours - Sprints 1-6 | Difference | [5 empty] | Resource | Product Releasae | % | Story points Total Available | Story points ask upto 4/15 | Prasob update points in this column if changes are needed in F
Core Data Services | Abdul Naik | GRID / GRID Adj. | 0 | 0 | 0 | 0 |  |  |  |  | Shared Services | Abhijith | PROOF BAU | 0.5 | 23.2 | 30 | -6.8
|  | IDC | 0.5 | 22 | 0 | 22 | [5 empty] | Abhijith | Adj | 0.4 | 18.56 | 1 | 17.56
|  | IDC2 | 0.25 | #N/A | 0 | #N/A | [5 empty] | Abhijith | IDC | 0.1 | 4.64 | 7 | -2.36
|  | DOS | 0.25 | #N/A | 0 | #N/A | [5 empty] | Abhijith | IDC2 | 0 | 0 |  | 0
| Anoop Mohan | GRID / GRID Adj. | 0.2 | 8.8 | 0 | 8.8 | [5 empty] | Prasob | PROOF | 0.4 | 18.56 | 7 | 11.56
|  | IDC | 0.5 | 22 | 0 | 22 | [5 empty] | Prasob | IDC2 | 0.6 | 27.84 | 32 | -4.16
|  | IDC2 | 0.2 | 8.8 | 0 | 8.8 | [5 empty] | Manoj | Adj | 0.8 | 37.76 | 15 | 22.76
|  | DOS | 0.1 | 4.4 | 0 | 4.4 | [5 empty] | Manoj | IDC2 | 0.2 | 9.44 | 5 | 4.44
| Aravind Syama Unni | GRID / GRID Adj. | 0 | #N/A | 0 | #N/A | [5 empty] | Manoj | PROOF | 0.8 | 37.76 | 10 | 27.76
|  | IDC | 0.5 | #N/A | 0 | #N/A | [5 empty] | Krishna | ADJ | 0.2 | 9.44 | 3 | 6.44
|  | IDC2 | 0 | #N/A | 0 | #N/A | [5 empty] | Krishna | IDC-2 | 0.8 | 37.76 | 36 | 1.76
|  | DOS | 0.5 | #N/A | 0 | #N/A | [5 empty] | Samba | ADJ | 1 | 47.2 | 17 | 30.2
| Dana Fillhart | GRID / GRID Adj. | 0.1 | #N/A | 0 | #N/A | [5 empty] | Swapna | IDC | 0.3 | 14.16 | 16 | -1.84
|  | IDC | 0 | #N/A | 0 | #N/A | [5 empty] | Swapna | IDC-2 | 0.2 | 9.44 | 10 | -0.56
|  | IDC2 | 0 | #N/A | 0 | #N/A | [5 empty] | Swapna | PROOF | 0.5 | 23.6 | 16 | 7.6
|  | DOS | 0.9 | #N/A | 0 | #N/A | [5 empty] | Shiju | PROOF BAU | 0.2 | 9.44 | 6 | 3.44
| Johnson Robin | GRID / GRID Adj. | 0.25 | #N/A | 0 | #N/A | [5 empty] | Shiju | IDC-2 | 0.8 | 37.76 | 30 | 7.76
|  | IDC | 0.25 | #N/A | 0 | #N/A | [5 empty] | Jagan | iRIDER | 0.2 | 9.44 | 4 | 5.44
|  | IDC 2 | 0 | #N/A | 0 | #N/A | [5 empty] | Jagan | PROOF | 0.8 | 37.76 | 33 | 4.76
|  | DOS | 0.5 | #N/A | 0 | #N/A | [5 empty] | Krishnaraj | IDC-2 | 0.7 | 33.04 | 20 | 13.04
| Krishnaraj Nagarajan | GRID / GRID Adj. | 0.5 | 13.2 | 0 | 13.2 | [5 empty] | Meraj | IDC | 0.4 | 18.88 | 13 | 5.88
|  | IDC | 0 | 0 | 0 | 0 | [5 empty] | Meraj | IDC-2 | 0.2 | 9.44 | 9 | 0.44
|  | IDC 2 | 0.5 | 13.2 | 0 | 13.2 | [5 empty] | Meraj | PROOF | 0.4 | 18.88 | 15 | 3.88
|  | DOS | 0 | 0 | 0 | 0
| Mala Nadar | GRID | 0 | 0 | 0 | 0
|  | IDC | 0.5 | 13.2 | 0 | 13.2
|  | IDC2 | 0 | 0 | 0 | 0
|  | DOS | 0.5 | 13.2 | 0 | 13.2
| Rahul Bishnoi | GRID | 0.25 | 6.6 | 0 | 6.6
|  | IDC | 0.5 | 13.2 | 0 | 13.2
|  | IDC 2 | 0 | 0 | 0 | 0
|  | DOS | 0.25 | 6.6 | 0 | 6.6
| Varun Sundar | GRID | 0 | 0 | 0 | 0
|  | IDC | 0.2 | 5.28 | 0 | 5.28
|  | IDC 2 | 0 | 0 | 0 | 0
|  | DOS | 0.8 | 21.12 | 0 | 21.12
| Vilasini Ganesan | GRID | 0.5 | 13.2 | 0 | 13.2
|  | IDC | 0.4 | 10.56 | 0 | 10.56
|  | IDC 2 | 0 | 0 | 0 | 0
|  | DOS | 0.1 | 2.64 | 0 | 2.64
| Ashish Chourey | GRID | 0.25 | 6.6 | 0 | 6.6
|  | IDC | 0.5 | 13.2 | 0 | 13.2
|  | IDC 2 | 0.25 | 6.6 | 0 | 6.6
|  | DOS | 0 | 0 | 0 | 0
| Vijay Amirtharaj | GRID | 0.4 | 10.56 | 0 | 10.56
|  | IDC | 0 | 0 | 0 | 0
|  | IDC 2 | 0 | 0 | 0 | 0
|  | DOS | 0.6 | 15.84 | 0 | 15.84
Sum of Story Points | Column Labels
Row Labels | Abdul Nathik Abdul Hanan Najjar <abdulnathik.abdulhanannajjar@metlife.com> | Abhijith Jayakumar <abhijith.jayakumar@metlife.com> | Anoop Mohandas Sheelarani <anoop.mohandas-sheelarani@metlife.com> | Jagadeesan Balasubramanian <jbalasubramanian1@metlife.com> | Krishna Chandar Kandula <krishna-chandar.kandula@metlife.com> | Krishnaraj Nagarajan <krishnaraj.nagarajan@metlife.com> | Lokeshwaran Sankar <lokeshwaran.sankar@metlife.com> | Manoj Madhavan <manoj.madhavan@metlife.com> | Meraj Husen Ansari <merajhusen.ansari@metlife.com> | Prasob Nambuthodiyil <prasob.nambuthodiyil@metlife.com> | Samba siva Rao Prudhivi <sambasivarao.prudhivi@metlife.com> | Shibu Swaminathan <shibu.swaminathan@metlife.com> | Shiju Mathew <shiju.mathew@metlife.com> | Swapna Madhu <swapna.madhu@metlife.com> | (blank) | Grand Total
ADJUI |  | 3 |  |  | 3 |  |  | 15 |  |  | 12 | 3 |  |  |  | 31
IDC |  | 7 | [6 empty] | 18 |  |  |  |  | 3 |  | 28
IDC-2 | 25 |  | 7 |  | 38 | 25 |  | 5 | 9 | 37 | 5 |  | 35 | 10 |  | 196
IRIDER |  |  |  | 4 | [7 empty] | 5 |  |  |  | 4
PROOF |  | 25 |  | 25 |  |  | 42 | 10 | 15 | 8 |  | 7 |  | 22 |  | 127
Grand Total | 25 | 35 | 7 | 29 | 41 | 25 | 42 | 30 | 42 | 45 | 17 | 15 | 35 | 35 |  | 423
Note on R6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Proof automation can be renamed to script verification and story points can be 1

## HistorySP
| DOS | GRID |  |  | The Ninjas
Sprint | Delivered Story Points | Delivered Story Points | Total Story Points |  |  | Sprint | velocity | capacity in hrs
74 | 70 | 51 | 121 |  |  | 39 |  | 445
75 | 102 | 66 | 168 |  |  | 40
76 | 150 | 68 | 218 |  |  | 41
77 | 148 | 88 | 236 |  | PI6 | 42 | 67 | 480
78 | 104 | 105 | 209 |  |  | 43 | 56 | 480
79 | 134 | 84 | 218 |  |  | 44 | 57 | 480 |  | Resource | Avg Story points per resource
80 | 136 | 88 | 224 |  |  | 45 | 60 | 480 | 60 | 8 | 7.5
[6 empty] | 46 | 54 | 480
|  |  | Resource | Avg Story points per resource |  | 47 | 57 | 480
|  | 199.1429 | 9 | 22.127 | PI7 | 48 | 75 | 680
[6 empty] | 49 | 74 | 666
|  | Considering holidays, timeoff, team story point capacity/sprint: | 185 |  |  | 50 | 73 | 617
[6 empty] | 51 | 76 | 638 |  | Resource | Avg Story points per resource
[6 empty] | 52 | 75 | 680 | 74.6 | 10 | 7.46
|  | GRID Allocation | 120
|  | DOS Allocation | 65 |  | PI 8 | 53 |  | 796
[6 empty] | 54 |  | 789
[6 empty] | 55 |  | 810
[6 empty] | 56 |  | 810
[6 empty] | 57 |  | 782
[6 empty] | 58 |  | 810

## ProgramPriorityFeatures
From Brian
| 1 | Testing and Deploying Master Data Synch
| 2 | Complete changes for Privates Placement Multi-Currency
| 3 | Complete UI and begin IT testing for Private Structured Credit
| 4 | Entitlement enhancements for Data and Documents separation
| 5 | Development for Residential Loans
| 6 | Implement Document Streaming
| 7 | Automate MIM Relationship Portal contacts
| 8 | Screen design for RE Equity (No Development)
SAMURAI |  |  | 6 sprints
|  | GRID IDC - BAU 2022.05 Release (May 2022) | 8
|  | GRID IDC - BAU 2022.06 Release (June 2022) | 8
|  | GRID IDC - BAU 2022.07 Release (July 2022) | 8
|  | GRID IDC - BAU 2022.08 Release (August 2022) | 5
|  | GRID - BAU 2022.05 Release (May 2022) | 8
|  | GRID - BAU 2022.06 Release (June 2022) | 8
|  | GRID - BAU 2022.07 Release (July 2022) | 8
|  | GRID - BAU 2022.08 Release (August 2022) | 5
| Feature | GRID Automated Data Validations - May 2022 | 35
|  | GRID Automated Data Validations - June 2022 | 15 |  |  |  |  | story | DOS - BAU 2022.05 Release (May 2022) - COML
|  | GRID Automated Data Validations - July 2022 | 15 |  |  |  |  | Task | Task1
|  | GRID Automated Data Validations - August 2022 | 5 |  |  |  |  | Task | Task2
|  | GRID QA Automation | 15 | [5 empty] | DOS - BAU 2022.05 Release (May 2022) - AGRI
|  | GRID: Reserve capacity for Next PI Planning, System Demo and Innovation | 8 | [5 empty] | DOS - BAU 2022.05 Release (May 2022) - Privates/PABS
|  | GRID/IDC Rewiring | 15 | [5 empty] | DOS - BAU 2022.05 Release (May 2022) - SIT
|  | GRID REI Historical Load | 8 | [5 empty] | DOS - BAU 2022.05 Release (May 2022) - UAT
|  | GRID/DOS/GRID Adj AM KT | 8
|  | GRID IDC AllVue | 10
|  | GRID ESG Star | 3
|  | GRID-Future State Data Project | 55
|  | GRID - IDC Data Project - Client Reporting | 15
|  | DOS - BAU 2022.05 Release (May 2022) | 15
|  | DOS - BAU 2022.06 Release (June 2022) | 20
|  | DOS - BAU 2022.07 Release (July 2022) | 20
|  | DOS - BAU 2022.08 Release (August 2022) | 20
|  | DOS Databricks Optimization | 8
|  | DOS Residential | 8
|  | DOS RE Equity | 8
|  | DOS QA Automation | 15
|  | DOS Release On Demand | 8
| Future State data project | DOS: Reserve capacity for Next PI Planning, System Demo and Innovation | 8
|  | DOS IDC Rewiring | 8
|  | DOS ESG Star | 3
|  | PROOF-Future State Data Project | 105 | 2nd sprint | 6th sprint
NINJA |  | PROOF: Reserve capacity for Next PI Planning, System Demo and Innovation | 8
|  | IDC: Phase 2 : Design part 1 | 7
|  | IDC: Phase 2: Implementation - Part 1 | 7 |  |  | 8
|  | IDC: Phase 2 -Implementation API for query designer | 21
|  | IDC: Phase 2 -Implementation of query designer db | 20
|  | IDC: Phase 2 -Implementation of Validation of Query Definition | 11
|  | IDC: Phase 2 - Implementation of query builder Wizard | 46
|  | IDC: Phase 2 - Implementation of Orchestration Automation | 42
|  | PROOF - BAU 2022.05 Release (May 2022) | 32
|  | PROOF - BAU 2022.06 Release (June 2022) | 27
|  | PROOF - BAU 2022.07 Release (July 2022) | 32
|  | PROOF - BAU 2022.08 Release (August 2022) | 15
|  | iRIDER - BAU 2022.05 Release (May 2022) | 8
|  | iRIDER - BAU 2022.06 Release (June 2022) | 8
|  | iRIDER - BAU 2022.07 Release (July 2022) | 8 |  |  | 528 | 105.6
|  | iRIDER - BAU 2022.08 Release (August 2022) | 8
|  | GRID Adjustments - BAU 2022.05 Release (May 2022) | 8
|  | GRID Adjustments - BAU 2022.06 Release (June 2022) | 8
|  | GRID Adjustments - BAU 2022.07 Release (July 2022) | 8
|  | GRID Adjustments - BAU 2022.08 Release (August 2022) | 8
|  | PROOF/IDC/iRIDER AM KT | 8
|  | PROOF QA Automation | 20
| Future State data project | PROOF-Future State Data Project | 105 | 2nd sprint | 6th sprint
|  | Proof - historical | 5
|  | Proof -allvue | 13
|  | PROOF - ESG Star | 8
|  | Data Project - Client Reporting | 0

## PI Commitments
[5 empty] | manual | manual | (auto populate) | manual ( H= J for beginning). Periodically(SOS) manually reduce | auto | manual |  |  |  |  | manual | manual | auto | auto (equally distributing) | [5 empty] | manual | manual | manual | << not being used>> | << not being used>>
ID | Title | Work Item Type | Assigned To | WSJF | Business Value | Effort | Size | Rem Effort | Remaining Size | Target Date | State | Commit | Category | Team | Start in | Deliver in | Duration | S1 | S2 | S3 | S4 | S5 | s6 | INT | QA | Prod | % Complete | Actual Business Value
| GRID IDC - BAU 2022.05 Release (May 2022) |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | S | 1 | 2 | 2 | 4 | 4 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
| GRID IDC - BAU 2022.06 Release (June 2022) |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | S | 1 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 |  |  |  | 0 | 0
| GRID IDC - BAU 2022.07 Release (July 2022) |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | S | 3 | 6 | 6 | 0 | 0 | 2 | 2 | 2 | 2 |  |  |  | 0 | 0
| GRID IDC - BAU 2022.08 Release (August 2022) |  |  |  | 8 | 1 | 5 | 1 | 5 |  | New | Commit | BAU | S | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  | 0 | 0
| GRID - BAU 2022.05 Release (May 2022) |  |  |  | 9 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | S | 1 | 2 | 2 | 4 | 4 | 0 | 0 | 0 | 0 |  |  |  | 0
| GRID - BAU 2022.06 Release (June 2022) |  |  |  | 9 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | S | 1 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 |  |  |  | 0
| GRID - BAU 2022.07 Release (July 2022) |  |  |  | 9 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | S | 3 | 6 | 6 | 0 | 0 | 2 | 2 | 2 | 2 |  |  |  | 0 | 0
| GRID - BAU 2022.08 Release (August 2022) |  |  |  | 9 | 1 | 5 | 1 | 5 |  | New | Commit | BAU | S | 5 | 6 | 6 | 0 | 0 | 0 | 0 | 2.5 | 2.5 |  |  |  | 0 | 0
| GRID Automated Data Validations - May 2022 |  |  |  | 9 | 6 | 30 | 6 | 30 |  | New | Commit | BAU | S | 1 | 2 | 2 | 15 | 15 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
| GRID Automated Data Validations - June 2022 |  |  |  | 8 | 3 | 15 | 3 | 15 |  | New | Commit | Tenant Onboarding | S | 2 | 4 | 4 | 0 | 5 | 5 | 5 | 0 | 0 |  |  |  | 0 | 0
| GRID Automated Data Validations - July 2022 |  |  |  | 8 | 3 | 15 | 3 | 15 |  | New | Commit | Tenant Onboarding | S | 3 | 6 | 6 | 0 | 0 | 3.75 | 3.75 | 3.75 | 3.75 |  |  |  | 0 | 0
| GRID Automated Data Validations - August 2022 |  |  |  | 6 | 1 | 5 | 1 | 5 |  | New | Commit | Framework | S | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  |  |  | 0 | 0
| GRID QA Automation |  |  |  | 8 | 3 | 15 | 3 | 15 |  | New | Commit | Tenant Onboarding | S | 3 | 6 | 6 | 0 | 0 | 3.75 | 3.75 | 3.75 | 3.75 |  |  |  | 0 | 0
| GRID: Reserve capacity for Next PI Planning, System Demo and Innovation |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | Framework | S | 5 | 6 | 6 | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  | 0 | 0
| GRID/IDC Rewiring |  |  |  | 7 | 3 | 15 | 3 | 15 |  | New | Commit | Framework | S | 1 | 6 | 6 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 |  |  |  | 0 | 0
| GRID REI Historical Load |  |  |  | 7 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | Framework | S | 1 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 |  |  |  | 0 | 0
| GRID/DOS/GRID Adj AM KT |  |  |  | 7 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BCP | S | 1 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 |  |  |  | 0 | 0
| GRID IDC AllVue |  |  |  | 7 | 2 | 10 | 2 | 10 |  | New | Commit | Framework | S | 1 | 4 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 0 | 0 |  |  |  | 0 | 0
| GRID ESG Star |  |  |  | 7 | 0.6 | 3 | 0.6 | 3 |  | New | Commit | Framework | S | 1 | 4 | 4 | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 0 |  |  |  | 0 | 0
| GRID-Future State Data Project-1 |  |  |  | 9 | 10 | 55 | 10 | 55 |  | New | Commit | Innovation | S | 2 | 5 | 5 | 0 | 13.75 | 13.75 | 13.75 | 13.75 | 0
| GRID-Future State Data Project - 2 |  |  |  | 9 | 4 | 20 | 4 | 20 |  | New | Commit | Innovation | S | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 20
| GRID - IDC Data Project - Client Reporting |  |  |  | 7 | 3 | 15 | 3 | 15 |  | New | Commit | BAU | S | 4 | 6 | 3 | 0 | 0 | 0 | 5 | 5 | 5 |  |  |  | 0 | 0
| DOS - BAU 2022.05 Release (May 2022) |  |  |  | 8 | 3 | 15 | 3 | 15 |  | New | Commit | BAU | S | 1 | 2 | 2 | 7.5 | 7.5 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
| DOS - BAU 2022.06 Release (June 2022) |  |  |  | 8 | 4 | 20 | 4 | 20 |  | New | Commit | BAU | S | 1 | 4 | 4 | 5 | 5 | 5 | 5 | 0 | 0 |  |  |  | 0 | 0
| DOS - BAU 2022.07 Release (July 2022) |  |  |  | 8 | 4 | 20 | 4 | 20 |  | New | Commit | BAU | S | 3 | 6 | 6 | 0 | 0 | 5 | 5 | 5 | 5 |  |  |  | 0 | 0
| DOS - BAU 2022.08 Release (August 2022) |  |  |  | 7 | 4 | 20 | 4 | 20 |  | New | Commit | Framework | S | 5 | 5 | 1 | 0 | 0 | 0 | 0 | 20 | 0 |  |  |  | 0 | 0
| DOS Databricks Optimization |  |  |  | 7 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | Framework | S | 1 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 |  |  |  | 0 | 0
| DOS Residential |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | Framework | S | 1 | 3 | 3 | 2.6667 | 2.6667 | 2.6667 | 0 | 0 | 0
| DOS RE Equity |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | Framework | S | 5 | 6 | 2 | 0 | 0 | 0 | 0 | 4 | 4
| DOS QA Automation |  |  |  | 9 | 3 | 15 | 3 | 15 |  | New | Commit | Framework | S | 1 | 6 | 6 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
| DOS Release On Demand |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | Framework | S | 5 | 6 | 2 | 0 | 0 | 0 | 0 | 4 | 4
| DOS: Reserve capacity for Next PI Planning, System Demo and Innovation |  |  |  | 6 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | S | 5 | 6 | 2 | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  | 0 | 0
| DOS IDC Rewiring |  |  |  | 7 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | S | 5 | 6 | 2 | 0 | 0 | 0 | 0 | 4 | 4 |  |  |  | 0 | 0
| DOS ESG Star |  |  |  | 7 | 0.6 | 3 | 0.6 | 3 |  | New | Commit | Framework | S | 2 | 4 | 3 | 0 | 1 | 1 | 1 | 0 | 0
| PROOF: Reserve capacity for Next PI Planning, System Demo and Innovation |  |  |  | 7 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | Framework | N | 2 | 3 | 2 | 0 | 4 | 4 | 0 | 0 | 0
| IDC: Phase 2 : Design part 1 |  |  |  | 6 | 1 | 5 | 1 | 5 |  | New | Commit | Framework | N | 1 | 6 | 6 | 0.83333 | 0.83333 | 0.83333 | 0.83333 | 0.83333 | 0.83333
| IDC: Phase 2: Implementation - Part 1 |  |  |  | 6 | 1 | 5 | 1 | 5 |  | New | Commit | Framework | N | 1 | 6 | 6 | 0.83333 | 0.83333 | 0.83333 | 0.83333 | 0.83333 | 0.83333
| IDC: Phase 2 -Implementation API for query designer |  |  |  | 9 | 4 | 20 | 4 | 20 |  | New | Commit | Framework | N | 1 | 6 | 6 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333
| IDC: Phase 2 -Implementation of query designer db |  |  |  | 9 | 4 | 20 | 4 | 20 |  | New | Commit | Framework | N | 1 | 6 | 6 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333 | 3.3333
| IDC: Phase 2 -Implementation of Validation of Query Definition |  |  |  | 7 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | Framework | N | 1 | 6 | 6 | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 1.3333
| IDC: Phase 2 - Implementation of query builder Wizard |  |  |  | 9 | 9 | 45 | 9 | 45 |  | New | Commit | Framework | N | 1 | 6 | 6 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 |  |  |  | 0 | 0
| IDC: Phase 2 - Implementation of Orchestration Automation |  |  |  | 9 | 8 | 40 | 8 | 40 |  | New | Commit | Framework | N | 1 | 6 | 6 | 6.6667 | 6.6667 | 6.6667 | 6.6667 | 6.6667 | 6.6667
| PROOF - BAU 2022.05 Release (May 2022) |  |  |  | 9 | 6 | 30 | 6 | 30 |  | New | Commit | BAU | N | 1 | 2 | 2 | 15 | 15 | 0 | 0 | 0 | 0 |  |  | 2022-05-21
| PROOF - BAU 2022.06 Release (June 2022) |  |  |  | 9 | 5 | 25 | 5 | 25 |  | New | Commit | BAU | N | 1 | 4 | 4 | 6.25 | 6.25 | 6.25 | 6.25 | 0 | 0 |  |  | 2022-06-18
| PROOF - BAU 2022.07 Release (July 2022) |  |  |  | 9 | 6 | 30 | 6 | 30 |  | New | Commit | BAU | N | 3 | 6 | 6 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 |  |  | 2022-07-16
| PROOF - BAU 2022.08 Release (August 2022) |  |  |  | 9 | 3 | 15 | 3 | 15 |  | New | Commit | BAU | N | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 15 | 0 |  |  | 2022-08-20
| GRID Adjustments - BAU 2022.05 Release (May 2022) |  |  |  | 9 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | N | 1 | 2 | 2 | 4 | 4 | 0 | 0 | 0 | 0 |  |  | 2022-05-21
| GRID Adjustments - BAU 2022.06 Release (June 2022) |  |  |  | 9 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | N | 1 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 |  |  | 2022-06-18
| GRID Adjustments - BAU 2022.07 Release (July 2022) |  |  |  | 5 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | N | 3 | 6 | 6 | 0 | 0 | 2 | 2 | 2 | 2 |  |  | 2022-07-16
| GRID Adjustments - BAU 2022.08 Release (August 2022) |  |  |  | 6 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | N | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  |  | 2022-08-20
| PROOF/IDC/iRIDER AM KT |  |  |  | 7 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BCP | N | 1 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0
| PROOF QA Automation |  |  |  | 9 | 6 | 30 | 6 | 30 |  | New | Commit | Framework | N | 1 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5
| PROOF-Future State Data Project - Part 1 |  |  |  | 9 | 9 | 45 | 9 | 45 |  | New | Commit | Business | N | 1 | 3 | 3 | 15 | 15 | 15 | 0 | 0 | 0
| PROOF-Future State Data Project - Part 2 |  |  |  | 9 | 8 | 40 | 8 | 40 |  | New | Commit | Business | N | 3 | 4 | 4 | 0 | 0 | 20 | 20 | 0 | 0
| Proof - historical |  |  |  | 9 | 1 | 5 | 1 | 5 |  | New | Commit | Business | N | 1 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 0
| Proof -allvue |  |  |  | 9 | 3 | 15 | 3 | 15 |  | New | Commit | Business | N | 1 | 6 | 6 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
| PROOF - ESG Star |  |  |  | 8 | 1 | 5 | 1 | 5 |  | New | Commit | Business | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| iRIDER - BAU 2022.05 Release (May 2022) |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | N | 1 | 2 | 2 | 4 | 4 | 0 | 0 | 0 | 0 |  |  | 2022-05-21
| iRIDER - BAU 2022.06 Release (June 2022) |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | N | 1 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 0 |  |  | 2022-06-18
| iRIDER - BAU 2022.07 Release (July 2022) |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | N | 3 | 6 | 6 | 0 | 0 | 2 | 2 | 2 | 2 |  |  | 2022-07-16
| iRIDER - BAU 2022.08 Release (August 2022) |  |  |  | 8 | 1.6 | 8 | 1.6 | 8 |  | New | Commit | BAU | N | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  |  | 2022-08-20
|  |  |  | Orig Effort Needed: |  |  | 0 | Current | 884 | Committed: | 61 | Stretch/vendor: | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | #VALUE! | #VALUE!
|  |  |  | Orig Effort Available |  |  | 837.52 | Fully Committed | 837.52 | Over Committed | Delivered |  | Total Items | [9 empty] | 0 |  |  |  | #VALUE! | #VALUE!
|  |  |  | Trend: |  |  | 3 |  | 0 |  | 0 |  | 0
`
[29 empty] | 0.2 | 1
[29 empty] | 0.4 | 2
[29 empty] | 0.6 | 3
[29 empty] | 0.8 | 4
[29 empty] | 1.6 | 8
[29 empty] | 1 | 5 | T
[29 empty] | 2 | 10 | CA
[29 empty] | 3 | 15 | H
[29 empty] | 4 | 20 | IM
[29 empty] | 5 | 25 | N
[29 empty] | 6 | 30 | S
[29 empty] | 7 | 35 | TB
[29 empty] | 8 | 40 | N
[29 empty] | 9 | 45 | S
[29 empty] | 10 | 55
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: manual ( H= J for beginning). Periodically manually reduce
Note on N2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: commit: - as per team, this will be done stretch - less confident; ongoing ongoing features - TBD

## Team
| PI Start date: |  | 2022-04-20 | Today's Date: | 2022-04-06
[14 empty] | Next steps |  |  |  | Owner |  |  | Due by
| Product Manager(s): Jatin Chauhan | [12 empty] | Create features in AzDO |  |  |  | Dana/Vilasini/Jagan |  | 100% | 2022-01-18
| Total Ask | Orig Eff | Team | Scrum Master | Product Owner | Team Size S1 | Team Size S2 | Team Size S3 | Team Size S4 | Team Size S5 | Team Size S6 |  |  | Create stories in AzDO |  |  |  | Dana/Vilasini/Jagan |  |  | 2022-01-20
| 0 | 445.76 | The Ninjas | Jagadeesan Balasubramanian | Jatin Chauhan | 10.3 | 11.4 | 11.14 | 11.5 | 11.38 | 11.38 |  |  | Create Objectives, risks, Question |  |  |  | Jatin/Dana/Vilasini/Jagan |  |  | 2022-01-18
| 0 | 391.76 | Samurai | Dana Fillhart | Jatin Chauhan | 9 | 9.9 | 10.05 | 9.7 | 10.32 | 10.25 |  |  | Size Available Vs Need |  |  |  | Vilasini |  |  | 2022-01-18
Assumption
[14 empty] | PROOF | 8 Story points assumed to be delivered by a team member in given sprint
| 0 | 837.52 | Totals |  |  | 19.3 | 21.3 | 21.19 | 21.2 | 21.7 | 21.63 |  |  | GRID/DOS | 8 Story points assumed to be delivered by a team member in given sprint
| Rem Ask | Rem Eff | Team | Product | Application Name(s) | Outlook |  | Deviation |  | S1: need | S1: avail | S2: need | S2: avail | S3: need | S3: avail | S4: need | S4: avail | S5: need | S5:avail | S6: need | S6:avail | Check need | Check avail
| 463 | 445.76 | The Ninjas |  | IRIDER, PROOF, IDC | Good | -17.24 | -3.868% | The Ninjas | 82.5833 | 82.4 | 86.5833 | 91.2 | 95.0833 | 89.12 | 76.0833 | 92 | 74.8333 | 91.04 | 42.8333 | 91.04 | 0 | 1
| 421 | 391.76 | Samurai |  | GRID, DOS | Over Utilized | -29.24 | -7.464% | Samurai | 56.4167 | 72 | 76.1667 | 79.2 | 62.1667 | 80.4 | 64.5 | 77.6 | 92.75 | 82.56 | 69 | 82 | 0 | 1
| 884 | 837.52 | Totals |  |  | Good | -46.48 | -5.55% |  | 139 | 154.4 | 162.75 | 170.4 | 157.25 | 169.52 | 140.5833 | 169.6 | 167.5833 | 173.6 | 111.8333 | 173.04
| Sprints Remaining |  | Sprint | Start | End | Days remaining
1 | 5 |  | 1 | 2022-04-20 | 2022-05-03 | 10
0 | Total Days Remaining |  | 2 | 2022-05-04 | 2022-05-17 | 10
0 | 50 |  | 3 | 2022-05-18 | 2022-05-31 | 10
0 | Sprint % Remaining |  | 4 | 2022-06-01 | 2022-06-14 | 10
0 | 100% |  | 5 | 2022-06-15 | 2022-06-28 | 10
|  |  | 6 | 2022-06-29 | 2022-07-12 | 10
Formulas:
Scrum Master = DATE(YEAR([Product Owner, row above]),MONTH([Product Owner, row above]), DAY([Product Owner, row above]) +1)
Product Owner = DATE(YEAR([Scrum Master]), MONTH([Scrum Master]), DAY([Scrum Master]) +13)
Team Size S1 = IF(AND(G1 >=[Scrum Master],G1<=[Product Owner]), IF((DATEDIF(G1,[Product Owner],"D")+1)>=11,(DATEDIF(G1,[Product Owner],"D")+1)-4, IF((DATEDIF(G1,[Product Owner],"D")+1)>=3, (DATEDIF(G1,[Product Owner],"D")+1)-2,(DATEDIF(G1,[Product Owner],"D")+1))),IF(G1>[Product Owner],0,10))

## Objectives(opt)
Assumptions and Dependencies
Sr. No. | Assumption/Questions/Dependencies | Action item
1 | MIM Digital Portal priority for Resi API Mapping
2 | Eng dependency for DOS containers for Resi | Darryl to confirm
3 | MIM Digital Portal priority/Source dependency for Multicurrency for Commercial | Brian to confirm dates
4 | GRID Adjustments - Eng Team dependency for PROD/DR and new Azure resources | Darryl to confirm
5 | GRID Data Validator (GDV) - OSS/GARB dependency | Architecture team (action item?)
6 | GRID Data Validator (GDV) - DevOps Dependency for making CICD readyf or each environment | Deva to confirm
Risks
Sr. No. | Risks | Action item
1 | Databricks pool implementation is very detailed and intrusive, need to ensure DOS is onboarded successfully without any impact, it will help with resource contraint on platform and improve performance
2 | Eng. And DevOps team dependency for GRID Data Validator new capability pipelines
3
Note - we need these features separated by app in other contexts, please separate your app in the Feature Numbers
Sr. No. | PI Objective - Jan 2022 | Feature Numbers | BV Owner | BV Score | What is being delivered, whats the value, for who, by when
1 | Deliver Commercial and AG asset class data domain related changes for MIS Refactoring program for Feb and Mar 2022 that will enable MIS application retirement for MIM business domain | GRID: DOS: 460402, 476563 PROOF: | Jatin | 7
2 | Onboard Residential asset class to GRID and DOS for Digital Data Platform and Portal through PROOF | GRID: DOS: 458720, 463287, 463288, 463289, 476561 PROOF: | Brian | 9
3 | Onboard Commercial, AG, Private Placement and Private ABS asset class data domain related changes to DOS per business requirement for month of Feb, Mar and Apr 2022, example Rewiring of contacts to pull from Salesforce | GRID: DOS: PABS: 456476 (Feb), 476531 (Mar), 476538 (Apr) PrPl: 456465 (Feb), 476530 (Mar), 476537 (Apr) Coml: 456443 (Feb), 476529 (Mar), 476533 (Apr) Agri: 456454 (Feb), 476528 (Mar), 476532 (Apr) Misc: 476543 (App Readiness Updates) PROOF: | Brian | 9
4 | Deliver enhancements to GRID Adjustments portal based on business user feedback | GRID: DOS: N/A PROOF: | GP | 7
5 | Enable automation of queries onboarding to IDC platform per consumer need through a rich UI that allows user to build query, see output and query data stored in GRID for given dataset | GRID: DOS: 473580 PROOF: | Jatin | 8
6 | Deliver fit for purpose data based on consumer needs through IDC with new queries onboarding or modification to existing queries including optimization of queries | GRID: DOS: N/A PROOF: | Jatin | 8
7 | Implement central data validation capability on top of Investments Data Lake (GRID) with detailed dashboards providing relevant information to data stewards, support and product teams and in turn help improve data quality on digital platforms | GRID: DOS: N/A PROOF: | Jatin | 8
8 | PROOF, GRID, DALFI, DOS, , IDC, IRIDER Tech Debt efforts and Optmization: Identify processes and code base needing optimization and fine tune to enhance overall data platform processes performance, SLA, data quality, delivery optimization, SPN+Cert+KV expiry management, DataBricks cluster pools and repo | GRID: DOS: 478268, 476539, 476564, 460322 PROOF: | Jatin | 7
9 | Continue hydrating lake with additional data domains that meets MIM client reporting, MMR, RE Equity, and SecLending business needs | GRID: DOS: 476583 (Pub. Corp. Analysis), 476566 (RE Eq. Analysis) PROOF: | Jatin | 6
10 | Deliver PROOF automated testing capability Phase 2 that will reduce manual testing efforts and improve code quality delivered to PROD env; Partially deliver automated testing efforts for GRID and DOS; | GRID: DOS: N/A (efforts done on PROOF side; DOS team to assist with testing) PROOF: | Jatin | 6
11 | IRIDER Feb, Mar, Apr releases to support Tenant application changes and BAU | GRID: DOS: N/A PROOF: | Jatin | 5

## Summary(not being used)
Count of ID | Column Labels
Category | H | IM | (blank) | Grand Total
BAU | 2 | 3 |  | 5
Innovation | 1 |  |  | 1
Data360 | 6 |  |  | 6
Power BI | 7 |  |  | 7
(blank)
Decom | 18 |  |  | 18
Grand Total | 34 | 3 |  | 37
Category-Team
Row Labels | H | IM | (blank) | Grand Total
BAU | 2 | 3 |  | 5
Innovation | 1 |  |  | 1
(blank)
Power BI | 7 |  |  | 7
Data360 | 6 |  |  | 6
Decom | 18 |  |  | 18
Grand Total | 34 | 3 |  | 37

## Raw Data(not being used)
Row Labels | Count of ID | Sum of % Complete | Sum of Planned Business Value | Sum of Actual Business Value
BAU | 5 | 3.5 | 28 | 15
Innovation | 1 | 0 | 7 | 0
Power BI | 7 | 1.25 | 49 | 0
(blank)
Data360 | 6 | 0.7 | 43 | 0
Decom | 18 | 0.93333 | 127 | 0
Grand Total | 37 | 6.3833 | 254 | 15
Category | Number of Features | Sum of % Complete | Percent complete |  | Category | % Planned | % Completed
BAU | 18 | 5.25 | 29.1667 | 100 | BAU | 100 | 29.1667
BHF | 2 | 0 | 0 | 100 | BHF | 100 | 0
CECL | 3 | 0.33333 | 11.1111 | 100 | CECL | 100 | 11.1111
Innovation | 8 | 0.66667 | 8.3333 | 100 | Innovation | 100 | 8.3333
InvestmentTypeClassification | 2 | 0 | 0 | 100 | InvestmentTypeClassification | 100 | 0
MIM-AIC | 3 | 1 | 33.3333 | 100 | MIM-AIC | 100 | 33.3333
Power BI | 7 | 1.25 | 17.8571 | 100 | Power BI | 100 | 17.8571
Support | 10 | 2.5833 | 25.8333 | 100 | Support | 100 | 25.8333
Data360 | 6 | 0.7 | 11.6667 | 100 | Data360 | 100 | 11.6667
Decom/Digital | 13 | 1.6167 | 12.4359 | 100 | Decom/Digital | 100 | 12.4359
Argus | 1 | 0 | 0 | 100 | Argus | 100 | 0
Tech Debt | 1 | 0.5 | 50 | 100 | Tech Debt | 100 | 50
Reporting | 3 | 0.25 | 8.3333 | 100 | Reporting | 100 | 8.3333
Compliance | 5 | 0.875 | 17.5 | 100 | Compliance | 100 | 17.5
TEBOW | 1 | 0.2 | 20 | 100 | TEBOW | 100 | 20
Decom | 38 | 0.33333 | 0.87719 | 100 | Decom | 100 | 0.87719
MIM | 2 | 0 | 0 | 100 | MIM | 100 | 0
OWS | 1 | 0 | 0 | 100 | OWS | 100 | 0
SOFR/SONIA | 4 | 0.5 | 12.5 | 100 | SOFR/SONIA | 100 | 12.5
Category | Sum of Planned Business Value | Sum of Delivered Business Value
BAU | 96 | 29
BHF | 15 | 0
CECL | 24 | 0
Innovation | 46 | 0
InvestmentTypeClassification | 16 | 0
MIM-AIC | 21 | 10
Power BI | 49 | 0
Support | 64 | 5
Data360 | 43 | 0
Decom/Digital | 88 | 0
Argus | 3 | 0
Tech Debt | 3 | 0
Reporting | 24 | 0
Compliance | 33 | 0
TEBOW | 7 | 0
Decom | 286 | 0
MIM | 9 | 0
OWS | 7 | 0
SOFR/SONIA | 28 | 0

## Sprint Goals
Team | Sprint | Sprint Goal (Determine what main focus/objective for your Sprint and should be subset into your PI Objectives) | Confidence Vote (1 lowest -5 highest)
The Ninjas | 2 | IDC Phase 2 | 3.4
The Ninjas | 3 | Adjustment UI | 5