## Functionalities
SL No | Functionality | Page | How to get here | Functionalities | Navigate To | UI | API | UI % Complete | API % Complete | Integration % Complete | UI - Days required to complete | API - Days required to complete | Database
1 | Show the List of Existing Queries based on selected filters | Query Designer Suggestion Page - Default Page | Default Page - On Site Load/Menu(IDC Queries) |  | Navigate to the Step 1 of the wizard. |  |  | 75 | 62.5
|  |  |  | a. Load DataClass |  |  | /dataclass | 100 | 100 | 100
|  |  |  | b. Load DataSystemCode based on dataClass |  |  | /datasetType?dataclass={dataclass} | 100 | 75 | 100
|  |  |  | c. Load DataFrame (Layer 1 and Layer 2) in same dropdown and Filter DataFrames on selecting DataClass and DataSystemCode |  |  | /dataframes?datasetType={}&dataClass={} | 100 | 75 | 100
|  |  |  | d. Load all the existing query(Approved) as query suggestion |  |  | /queries/search?dataframes={dataframe1,dataframe2} |  | 0 |  | 0.5 | 4
|  |  |  | e. Show All queries(Including Rejected Query) on selecting the checkbox. | [6 empty] | 0.5 | 0.25
|  |  |  | f. Allow user to View the existing query |  |  | /queries/{queryname}/{Version} |  | 0 |  | 1 | 5
|  |  |  | g. Reject the suggestion and navigate to design new query | [6 empty] | 1 | 1.5
2 | Query Design | Default Page - First section/Step 1 | Only from Query Suggestion section |  | Navigate to the Step 2 of the wizard to select the source parameters. Cancel will go to Query Suggestion screen |  |  |  | 0
|  |  |  | a. QueryName and Query Description - Input Field, EAI Code - Dropdown(Single Select) | [6 empty] | 2
b. DataClass and DataSystemCode - Filters to filter the DataFrame
c. DataFrame - Dropdown with Grid DataFrames and IDC DDFs(Single Select)
d.Load all subnodes of dataframe in a dropdown
d. Alias Name for the selected DataFrame - Input Field
|  |  |  | c. Add button - Click will Add the DataFrame as a Source in the Query | [6 empty] | 0.5
|  |  |  | e. A card with DataFrame basic info will be visible | [6 empty] | 1
|  |  |  | f. User can add more than DataFrame as a source of the query | [6 empty] | 1
|  |  |  | g. cards will be connected with each other indicating the join between the DataFrames | [6 empty] | 0.5
|  |  |  | h. Button - Save and Continue will create the source section of the query. Cancel will cancel and go back to the previous screen. |  |  | /queries/{queryName}/{version}/schema |  | 0 |  | 2 | 2
3 | Query Design | Default Page - First section/Step 1 | Only from Query Suggestion section | Existing Query - Options(View or Edit Query) | Navigate to the Step 2 of the wizard to select the source parameters. Cancel will go to Query Suggestion screen
|  |  |  | a. QueryName, Query Version and EAI Code - Label | [6 empty] | 1
b. DataClass and DataSystemCode - Filters to filter the DataFrame
c. DataFrame - Dropdown with Grid DataFrames and IDC DDFs(Single Select)
d. Alias Name for the selected DataFrame - Input Field
|  |  |  | c. Add button - Click will Add the DataFrame as a Source in the Query | [6 empty] | 1
|  |  |  | e. A card with DataFrame basic info will be visible | [6 empty] | 0
|  |  |  | f. User can add more than DataFrame as a source of the query | [6 empty] | 0
|  |  |  | g. cards will be connected with each other indicating the join between the DataFrames | [6 empty] | 0
|  |  |  | h. Option(View Query) -> Buttons -> Validate and Execute, Submit Query for Approval and Back |  |  | /requests |  | 50 |  | 1
|  |  |  | i. Right side pane will be visible displaying the query details(Read Only) Source, Output Fields, Joins, Filters. | [6 empty] | 1
|  |  |  | k. Option(Edit Query) -> Buttons -> Save and Continue, Cancel |  |  | /queries/{queryName}/{version}/schema |  | 0 |  | 2
4 | Source Parameters | Query Wizard Step 2 | Only from Step 1 of the Wizard |  | Navigate to the first Step 3 of the wizard to select the Create Pre Triggers. Previous Step will go to the Query Source Step. Cancel will go to Query Suggestion screen
|  |  |  | a. Dropdown that loads all the DataFrame part of the Source of the query(Single Select) | [6 empty] | 1.5
b. Dropdown for Region, Period, Payload Tag, Payload Type, Fallbacktopreviousdate(True/False) and AsOfDate(Date Selector) (Single Select)
c. Select DataFrame, complete the source parameter selection.Period is mandatory single select field?Click Add
d. Only one entry per DataFrame
e. Change DataFrame to enter for other DataFrames
|  |  |  | f. Button -> Save and Continue, Previous Step and Cancel |  |  | /queries/{queryName}/{version}/schema |  | 0
5 | Create PreTrigger | Query Wizard Step 3 | Only from Step 2 of the Wizard |  | Navigate to the first Step 4 of the wizard to create Joins. Previous Step will go to the Source Parameter. Cancel will go to Query Suggestion screen
|  |  |  | a. Tabular format | [6 empty] | 1.5
b. Row 1: Each DataFrame part of the source will be in a cell
|  |  |  | c. Row 2:Region Dropdown populating All Regions specific to the DataFrame. If the user has selected a region from the source parameter section then the dropdown will have only one region locked and available in this section. |  |  | /dataframes/{dataFrameName} |  | 100
|  |  |  | d. Row 2:Period Dropdown populating All Period specific to the DataFrame. If the user has selected a period from the source parameter section then the dropdown will have only one period locked and available in this section. |  |  | /dataframes/{dataFrameName} |  | 100
e. Row 2:PayloadTag Dropdown populating All Payload specific to the DataFrame. If the user has selected a Payload from the source parameter section then the dropdown will have only one Payload locked and available in this section.
f. clicking Add button will create the Pre Trigger and the wizard screen will allow the user to create all possible Pre Trigger conditions.
g. Grid that shows the Existing/New Joins created for the query
|  |  |  | h. Button -> Save and Continue, Previous Step and Cancel |  |  | /queries/{queryName}/{version}/schema |  | 0
6 | Joins | Query Wizard Step 4 | Only from Step 3 of the Wizard |  | Navigate to the Step 5 of the wizard to output fields. Previous Step will go to the Pre Tigger Step. Cancel will go to Query Suggestion screen
|  |  |  | a. LeftDataFrame Dropdown will populate Source DataFrames(Single Select) | [6 empty] | 2.5
b. RightDataFrame Dropdown will populate Source DataFrames(Single Select)
c. Selecting DataFrame from Left Dropdown will load the Field specific to the DataFrame in Dropdown(Single Select)
d. Selecting DataFrame from Right Dropdown will load the Field specific to the DataFrame in Dropdown(Single Select)
e. Dropdown to select Join Type(INNER, LEFT OUTER, RIGHT OUTER)
f. Textbox - To create Join Expression
g. Add button to Add a Join Entry
h. Grid that shows the Existing/New Joins created for the query
i. Button -> Save and Continue, Previous Step and Cancel
7 | Output Fields | Query Wizard Step 5 | Only from Step 4 of the Wizard |  | Navigate to the Step 6 of the wizard to field Filters. Previous Step will go to the Joins Step. Cancel will go to Query Suggestion screen
|  |  |  | a. Dropdown that loads all the DataFrame part of the Source of the query(Single Select) | [6 empty] | 1.5
b. Selecting the Dropdown will load the fields specific to the selected dataframe in a grid
c. checkbox on the first cell to select the field for output
d. Button -> Save and Continue, Previous Step and Cancel
8 | Field Filters | Query Wizard Step 6 | Only from Step 5 of the Wizard | Output Fields | Previous Step will go to the Output Fields Step. Cancel will go to Query Suggestion screen
|  |  |  | a. Dropdown that loads all the DataFrame part of the Source of the query(Single Select) | [6 empty] | 2
b. Selecting the Dropdown will load the fields specific to the selected dataframe in a dropdown
c. Dropdown to load the Field operators(Equal To, Like, IN)
e. Default Value or Parameter Name - Text box to enter
f. ParameterType - Dropdown to load the DataType(String, Numeric, Decimal, Date)
g. Grid that shows the Existing/New Filters created for the query
i. Button -> Validate and Execute(Involved Notification to user on Validation Status and Data Available for Preview), Submit For Approval(Enabled after successful validation), Previous Step and Cancel
9 | Query Progress | Separate Screen - Load Query specific to the user | Navigation Menu |  | First step of the query wizard
|  |  |  | a. Show the list of queries created by the logged in user in grid | [6 empty] | 1.5
b. Grid cell shows the current query status
|  |  |  | c. Clicking on continue button of the query in the row will navigate to the wizard to the step 1 | [6 empty] | 2
|  |  |  | d. User will be allowed to continue from where they have left off. | [6 empty] | 1
10 | Adhoc Query | Separate Screen | Navigation Menu |  | NA
|  |  |  | a. Dropdown loads all the Layer 1/Grid DataFrames(single Select) | [6 empty] | 1
|  |  |  | b. Select the DataFrame | [6 empty] | 0
|  |  |  | c. Click View Data | [6 empty] | 1.5
d. Grid that load the Data(ReadOnly) of the DataFrame from the Parquet file. As it is Data. 50 Rows
11 | Query Approval | Separate Screen | Navigation Menu |  | NA
|  |  |  | a. Show list of queries that are pending for approval |  |  | /queries?status={status1,status2} |  | 100 |  | 1
|  |  |  | b. Toggle dropdown to show approved queries | [6 empty] | 0.5
|  |  |  | c. Pending approval queries can be approved, rejected(Reason is mandatory), abandon((Reason is mandatory)). | [6 empty] | 0.5
|  |  |  | d.Query approval Notification will be sent to the user | [6 empty] | 1
|  |  |  | e. Approved query(Json file) can be downloaded along with the query execution evidence(Excel file) digitally signed and downloaded to a zip file | [6 empty] | 1
12 | SIT | NA | NA |  | NA
13 | UAT | NA | NA |  | NA
14 | Admin Page | Separate Screen | Navigation Menu | Manage UI/Functionality specific user roles | NA |  |  |  | 0
15 | Historical Page | Separate Screen | Navigation Menu | Page to show the Query History | NA |  |  |  | 0

## Project Timeline
1.3.2.21 | Milestone: IDC Phase 2 for Query Builder Automation | 2022-02-15 | 2022-06-30 | 15% | In-Progress | Jatin Chauhan
1.3.2.21.1 | IDC Phase 2 design | 2022-02-15 | 2022-04-15 | 80% | In-Progress | Jatin Chauhan
1.3.2.21.2 | IDC Phase 2 development | 2022-03-10 | 2022-05-23 | 22% | In-Progress | Jatin Chauhan
1.3.2.21.3 | IDC Phase 2 SIT | 2022-05-24 | 2022-06-13 | 0% | Not Started | Jatin Chauhan
1.3.2.21.4 | IDC Phase 2 UAT | 2022-06-14 | 2022-06-27 | 0% | Not Started | Jatin Chauhan
1.3.2.21.5 | IDC Phase 2 PROD Deployment | 2022-06-30 | 2022-06-30 | 0% | Not Started | Jatin Chauhan

## API Specfications
IDC Phase 2 API Specifications
Roles : | [12 empty] | Completed | 6
| IDCDataReader | Read all IDC meta data and grid parquee data, IDCMetaDataReader | [10 empty] | Pending | 14
| IDCApprover | Approve IDC query definition | [10 empty] | InProgress | 2
| IDCDesigner | Edit IDC meta data | [10 empty] | Total | 22
SL No | Resource | API | HTTP Methods and permissions | [7 empty] | Coding Standards | Development Status
|  |  | POST | Permission | GET | Permission | PUT | Permission | DELETE | Permission | Controller
1 | Query | /queries/search?status={status1,status2} | Create a new query | IDCDesigner | Retrieve All queries based on status with latest status log | IDCDataReader | Bulk update of queries |  | Remove all queries |  | QueryDefinition | Completed
/queries/search?dataframes={dataframe1,dataframe2}&status={status1,status2}
2 | Query | /queries/{queryname}/{Version} latest | NA |  | Retrieve the details of query for {queryname}/{Version} - version not mandatory with latest status log | IDCDataReader | Update the details of query definition of {queryname}/{Version} if it exists | IDCDesigner | Delete query definition |  | QueryStatus | Completed
3 | Query | /queries/{queryname}/{Version}/status | Create a new status for the query- Approve query | IDCApprover | Retrieve the details of query with full status log {queryname}/{Version} | IDCDataReader | Update the logmessage column of query status | IDCDesigner | Delete query definition status 1 |  | QueryMeta | Pending
4 | Query | /queries/{queryname}/{Version}/metadata | Create Query output,join and filter | IDCDesigner | Get all meta data information about a query | IDCDataReader | Bulk update of queries |  | NA |  | QueryMeta | Pending
5 | Query | /queries/{queryName}/{Version}/metadata/queryJoin | Create query join for a query | IDCDesigner | Get query join for a query | IDCDataReader | Update query join for a query | IDCDesigner | NA |  | QueryMeta | Pending
6 | Query | /queries/{queryName}/{Version}/metadata/queryFilter | Create a filter for a query | IDCDesigner | Get filter for a query | IDCDataReader | Update filter for a query | IDCDesigner | NA |  | QueryMeta | Pending
7 | Query | /queries/{queryName}/{Version}/metadata/queryOutput | Create an output for a query | IDCDesigner | Get output for a query | IDCDataReader | Update output for a query | IDCDesigner | NA |  | QueryMeta | Pending
8 | Query | /queries/{queryName}/{version}/schema | Create schema for a query by passing join,filter and output as parameter in a single model | IDCDesigner | Get schema for a query | IDCDataReader | Update schema for a query | IDCDesigner | NA |  | QuerySchema | Pending
9 | Query | /queries/{queryName}/{version}/available?asofdate={}&period{}&region={} | NA |  | Does query have results available for given as-of-date, period, region | IDCDataReader | NA |  | NA |  | QueryReadiness | Pending
10 | Query | /queries/{queryname}/{Version}/subscription | Create a new permission for the query | IDCDesigner | Retrive permission of query {queryname}/{Version} | IDCDataReader | NA |  | Delete permission of query {queryname}/{Version} |  | QuerySubscription | Pending
11 | Query | /queries/{queryname}/{version}/download | NA |  | Download query and evidences in a zip file with signature | IDCDataReader | NA |  | NA |  | QueryDownload | InProgress
12 | Query | /queries/{queryname}/{version}/upload | Validate signature and extract zip file |  | NA |  | NA |  | NA |  | QueryUpload | Pending
13 | DataFrames | /dataframes?datasetType={}&dataClass={} | NA |  | Get all dataframes based on datasetType and dataClass | IDCDataReader | NA |  | NA |  | DataFrameMeta | Completed
14 | DataFrames | /dataframes/{dataFrameName} | Error |  | Retrieve the details of dataframe | IDCDataReader | NA |  | NA |  | DataFrameMeta | Pending
15 | DataFrames | /dataframes/{dataFrameName}/queries | Error |  | Retrieve all queries using {dataFrameName} | IDCDataReader | NA |  | NA |  | DataFrameQuery | Pending
16 | DataFrames | /dataframes/{dataFrameName}/data | NA |  | Read pq file from datalake max asofdate,region,period - Security? | IDCDataReader | NA |  | NA |  | DataFrames | Completed
17 | Requests | /requests | execute a new query ? GET | IDCDataReader | returns list of request IDs along with status of request (in-progress, completed, failed) | IDCDataReader | Bulk update of query instances |  | Remove all query instances |  | Request | InProgress
18 | Requests | /requests/{queryName}/{Version} | Error |  | Return list of exection evidence with status | IDCDataReader | NA |  | NA |  | RequestMeta | Pending
19 | Requests | /requests/{queryName}/{Version}/status | NA |  | Return details of query instance status log | IDCDataReader | NA |  | NA |  | RequestMeta | Pending
20 | Requests | /notification/ <Yet to finalize> | [9 empty] | Pending
21 | DataClass | /dataclass | NA |  | Return list of dataclasses active | IDCDataReader | NA |  | NA |  | DataClass | Completed
22 | DatasetType | /datasetType?dataclass={dataclass1, dataclass2} | NA |  | Return list of datasetTypes based on dataClass | IDCDataReader | NA |  | NA |  | DatasetType | Completed